## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Master
| Table 1 | Master
Totals
| Table 1 | Totals
Actual vs Projected
| Table 1 | Actual vs Projected
Start Date
| Table 1 | Start Date
wrk wk
| Table 1 | wrk wk

## Master
Project | Job# | Sales | Design | PM | Status | Contract Ttl | # wks in design | design $/wk | # wks in prod. | prod. $/wk | DA Date | Contract Date | Lead Testing Date | Lead Test Filed | # Draws | Project Launch Date | Estimate Days | CO Days | Actual Days | Sub Comp Date | Days to SubComp | FCO Date | Days SubComp to FCO | OCO Date | Days FCO to OCO | GQ score | Daily Log Goal | Daily Log Did | Photos Goal | Photos Did | Schedule Goal | Schedule Did | Average Score | Left Blank | 12/18/17-12/24/17 | 12/25/01-12/31/17 | 01/01/02-01/07/18 | 01/08/02-01/14/18 | 01/15/02-01/21/18 | 01/22/02-01/28/18 | 01/29/02-02/04/18 | 02/05/02-02/11/18 | 02/12/02-02/18/18 | 02/19/02-02/25/18 | 02/26/02-03/04/18 | 03/05/02-03/11/18 | 03/12/02-03/18/18 | 03/19/02-03/25/18 | 03/26/02-04/01/18 | 04/02/02-04/08/18 | 04/09/02-04/15/18 | 04/16/02-04/22/18 | 04/23/02-04/29/18 | 04/30/02-05/06/18 | 05/07/02-05/13/18 | 05/14/02-05/20/18 | 05/21/02-05/27/18 | 05/28/02-06/03/18 | 06/04/02-06/10/18 | 06/11/02-06/17/18 | 06/18/02-06/24/18 | 06/25/02-07/01/18 | 07/02/02-07/08/18 | 07/09/02-07/15/18 | 07/16/18-07/22/18 | 07/23/18-07/29/18 | 07/30/18-08/05/18 | 08/06/18-08/12/18 | 08/13/18-08/19/18 | 08/20/18-08/26/18 | 08/27/18-09/02/18 | 09/03/18-09/09/18 | 09/10/18-09/16/18 | 09/17/18-09/23/18 | 09/24/18-09/30/18 | 10/01/18-10/07/18 | 10/08/18-10/14/18 | 10/15/18-10/21/18 | 10/22/18-10/28/18 | 10/29/18-11/04/18 | 11/05/18-11/11/18 | 11/12/18-11/18/18 | 11/19/18-11/25/18 | 11/26/18-12/02/18 |  | 12/10/18-12/16/18 | 12/17/18-12/23/18 | 12/24/18-12/30/18 | 12/31/18-01/06/19 | 01/07/19-01/13/19 | 01/14/19-01/20/19 | 01/21/19-01/27/19 | 01/28/19-02/03/19 | 02/04/19-02/10/19 | 02/11/19-02/17/19 | 02/18/19-02/24/19 | 02/25/19-03/03/19 | 03/04/19-03/10/19 | 03/11/19-03/17/19 | 03/18/19-03/24/19 | 03/25/19-03/31/19 | 04/01/19-04/07/19 | 04/08/19-04/14/19 | 04/15/19-04/21/19 | 04/22/19-04/28/19 | 04/29/19-05/05/19 | 05/06/19-05/12/19 | 05/13/19-05/19/19 | 05/20/19-05/26/19 | 05/27/19-06/02/19 | 06/03/19-06/09/19 | 06/10/19-06/16/19 | 06/17/19-06/23/19 | 06/24/19-06/30/19 | 07/01/19-07/07/19 | 07/08/19-07/14/19 | 07/15/19-07/21/19 | 07/22/19-07/28/19 | 07/29/19-08/04/19 | 08/05/19-08/11/19 | 08/12/19-08/18/19 | 08/19/19-08/25/19 | 08/26/19-09/01/19 | 09/02/19-09/08/19 | 09/09/19-09/15/19 | 09/16/19-09/22/19 | 09/23/19-09/29/19 | 09/30/19-10/06/19 | 10/07/19-10/13/19 | 10/14/19-10/20/19 | 10/21/19-10/27/19 | 10/28/19-11/03/19 | 11/04/19-11/10/19 | 11/11/19-11/17/19 | 11/18/19-11/24/19 | 11/25/19-12/01/19 | 12/02/19-12/08/19 | 12/09/19-12/15/19 | 12/16/19-12/22/19 | 12/23/19-12/29/19 | 12/30/19-01/05/20 | 01/06/20-01/12/20 | 01/13/20-01/19/20 | 01/20/20-01/26/20 | 01/27/20-02/02/20
[35 empty] | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 |  | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 |  |  |  |  | 1581
Wangler (Grandview Heights) | 5090 | RR | LW | RL | CC | 277910 | 12 | 23.1592 | 21 | 13.2338 | 2018-12-05 | 2019-03-27 |  | 2004-09-23 | 5 | 2019-06-05 | 105 |  |  | 2019-10-11 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 105 | 0 | 0% | [52 empty] | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | [15 empty] | 277910 | 5.8208e-11
Masten (Dublin) | 6105 | JB | OKM | JJ | CC | 88637 | 12 | 7.3864 | 9 | 9.8486 | 2019-04-05 | 2019-06-24 |  |  | 5 | 2019-08-14 | 45 |  |  | 2019-10-10 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 45 | 0 | 0% | [52 empty] | 14: x; 15: x; 16: x; 17: x; 18: x; 19: x; 20: x; 21: x; 22: x; 23: x; 24: x; 25: x; 26: 1x; 27: 2x; 28: 3x; 29: 4x; 30: 5x; 31: 6x; 32: 9.8486; 33: 9.8486; 34: 9.8486; 35: 9.8486; 36: 9.8486; 37: 9.8486; 38: 9.8486; 39: 9.8486; 40: 9.8486 |  |  |  |  | 88637 | 0
Bernard (Worthington) | 5134 | RR | OKM | MF | CC | 65950 | 15 | 4.3967 | 8 | 8.2438 | 2019-02-27 | 2019-06-12 |  |  | 4 | 2019-08-23 | 40 |  |  | 2019-10-11 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 40 | 0 | 0% | [61 empty] | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 4.6x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 8.2438 | 8.2438 | 8.2438 | 8.2438 | 8.2438 | 8.2438 | 8.2438 | 8.2438 | [17 empty] | 65950 | 0
Abood | 5221 | RR |  | MS | CC | 8300 | 0 |  | 3 | 2.7667 |  | 2019-08-15 | N/A | N/A | 1 | 2019-09-18 | 15 |  |  | 2019-10-03 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 15 | 0 | 0% | [52 empty] | 32: CC; 33: 1x; 34: 2.7667; 35: 2.7667; 36: 2.7667 |  |  |  |  | 8300 | 0
Rudavsky | 4282 | JC | ASM | MS | CC | 12281.14 | 0 |  | 3 | 4.0937 |  | 2019-06-16 | N/A | N/A | 3 | 2019-09-04 | 15 |  |  | 2019-09-19 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 15 | 0 | 0% | [52 empty] | 27: x; 28: x; 29: x; 30: x; 31: x; 32: CC; 33: x; 34: x; 35: 4.0937; 36: 4.0937; 37: 4.0937 |  |  |  |  | 12281.14 | 1.819e-12
Rencheck | 3941 | JS | ASM | MS | CC | 29579 | 0 |  | 3 | 9.8597 |  | 2019-08-19 | N/A | N/A | 2 | 2019-09-04 | 15 |  |  | 2019-09-19 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 15 | 0 | 0% | [52 empty] | 27: x; 28: x; 29: x; 30: x; 31: x; 32: CC; 33: x; 34: x; 35: 9.8597; 36: 9.8597; 37: 9.8597 |  |  |  |  | 29579 | 0
Paider/Switz | 4251 | JC | OKM | RL | CC | 119142 | 8 | 14.8927 | 12 | 9.9285 | 2019-04-14 | 2019-07-19 |  |  | 4 | 2019-09-09 | 84 |  |  | 2019-12-02 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 84 | 0 | 0% | [52 empty] | 21: x; 22: x; 23: x; 24: x; 25: x; 26: x; 27: x; 28: CC; 29: 1x; 30: 2x; 31: 3x; 32: 4x; 33: 5x; 34: 6x; 35: 1x; 36: 9.9285; 37: 9.9285; 38: 9.9285; 39: 9.9285; 40: 9.9285; 41: 9.9285; 42: 9.9285; 43: 9.9285; 44: 9.9285; 45: 9.9285; 46: 9.9285; 47: 9.9285 |  |  |  |  | 119142 | 0
Pup Town Lounge (Kenny Rd remodel) | 3924 | RR | LW | EI | CC | 270680 | 18 | 15.0378 | 16 | 16.9175 |  | 2019-06-25 |  |  | 5 | 2019-09-09 | 112 |  |  | 2019-12-30 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 112 | 0 | 0% | [62 empty] | 11.1x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 14x | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | 16.9175 | [6 empty] | 270680 | 5.8208e-11
Musetti / Johnson | 5155 | RR | ASM | MF | CC | 67753 | 12 | 5.6461 | 8 | 8.4691 | 2019-05-14 | 2019-07-30 |  |  | 3 | 2019-09-18 | 56 |  |  | 2019-11-13 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 56 | 0 | 0% | [52 empty] | 19: x; 20: x; 21: x; 22: x; 23: x; 24: x; 25: x; 26: x; 27: x; 28: x; 29: CC; 30: 1x; 31: 2x; 32: 3x; 33: 4x; 34: 5x; 35: 6x; 36: 7x; 37: 8.4691; 38: 8.4691; 39: 8.4691; 40: 8.4691; 41: 8.4691; 42: 8.4691; 43: 8.4691; 44: 8.4691 |  |  |  |  | 67753 | 0
Kirkland | 5149 | RR | LW | JJ | CC | 98687 | 11 | 8.9715 | 10 | 9.8687 | 2019-05-01 | 2019-07-31 |  |  | 3 | 2019-10-14 | 70 |  |  | 2019-12-23 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 70 | 0 | 0% | [52 empty] | 17: x; 18: x; 19: x; 20: x; 21: x; 22: x; 23: x; 24: x; 25: x; 26: x; 27: CC; 28: CC; 29: CC; 30: 1x; 31: 2x; 32: 3x; 33: 4x; 34: 5x; 35: 6x; 36: 7x; 37: 8x; 38: 9x; 39: 10x; 40: 11x; 41: 9.8687; 42: 9.8687; 43: 9.8687; 44: 9.8687; 45: 9.8687; 46: 9.8687; 47: 9.8687; 48: 9.8687; 49: 9.8687; 50: 9.8687 |  |  |  |  | 98687 | -2.9104e-11
Petrelli/Hunt | 6104 | JB | LW | MF | CC | 187305 | 11 | 17.0277 | 16 | 11.7066 | 2019-04-03 | 2019-07-26 |  |  | 4 | 2019-09-25 | 112 |  |  | 2020-01-15 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 112 | 0 | 0% | [71 empty] | x | x | x | x | x | x | x | x | x | x | x | 3x | 4x | CC | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 | 11.7066 |  |  |  | 187305 | 2.9104e-11
Johnson | 5197 | RR | ASM | JJ | CC | 78245 | 6 | 13.0408 | 8 | 9.7806 | 2019-07-08 | 2019-08-29 |  |  | 2 | 2019-09-25 | 56 |  |  | 2019-11-20 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 56 | 0 | 0% | [52 empty] | 27: x; 28: x; 29: x; 30: x; 31: x; 32: x; 33: CC; 34: 1x; 35: 2x; 36: 3x; 37: 4x; 38: 5x; 39: 6x; 40: 9.7806; 41: 9.7806; 42: 9.7806; 43: 9.7806; 44: 9.7806; 45: 9.7806; 46: 9.7806; 47: 9.7806 |  |  |  |  | 78245 | 0
Stephen | 5214 | RR | ASM | EI | CC | 55000 | 10 | 5.5 | 6 | 9.1667 | 8/0919 | [5 empty] | 42 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 42 | 0 | 0% | [52 empty] | 36: CC; 37: 1x; 38: 2x; 39: 3x; 40: 4x; 41: 5x; 42: 9.1667; 43: 9.1667; 44: 9.1667; 45: 9.1667; 46: 9.1667; 47: 9.1667 |  |  |  |  | 55000 | 7.276e-12
Elmore | 4292 | JC |  | JJ | CC | 55000 | 10 | 5.5 | 4 | 13.75 | [6 empty] | 28 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 28 | 0 | 0% | [52 empty] | 36: CC; 37: 1x; 38: 13.75; 39: 13.75; 40: 13.75; 41: 13.75 |  |  |  |  | 55000 | 0
McKelvey | 6115 | JB | OKM | RL | CC | 42500 | 10 | 4.25 | 5 | 8.5 | 2019-04-26 | [5 empty] | 35 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 35 | 0 | 0% | [52 empty] | 20: x; 21: 4.3x; 22: 4.3x; 23: 4.3x; 24: 4.3x; 25: 4.3x; 26: 4.3x; 27: 4.3x; 28: 4.3x; 29: x; 30: x; 31: x; 32: CC; 33: 1x; 34: CC; 35: CC; 36: 1x; 37: 2x; 38: 3x; 39: 4x; 40: 5x; 41: 6x; 42: 8.5; 43: 8.5; 44: 8.5; 45: 8.5; 46: 8.5 |  |  |  |  | 42500 | 0
Presley | 4247 | JC | LW | EI | CC | 190282 | 10 | 19.0282 | 15 | 12.6855 | 2019-05-21 | 2019-08-30 |  |  | 5 | 2019-10-30 | 105 |  |  | 2020-02-12 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 105 | 0 | 0% | [52 empty] | 20: x; 21: x; 22: x; 23: x; 24: x; 25: x; 26: x; 27: x; 28: x; 29: x; 30: x; 31: CC; 32: CC; 33: 1x; 34: 2x; 35: 3x; 36: 4x; 37: 5x; 38: 6x; 39: 7x; 40: 8x; 41: 9x; 42: 10x; 43: 12.6855; 44: 12.6855; 45: 12.6855; 46: 12.6855; 47: 12.6855; 48: 12.6855; 49: 12.6855; 50: 12.6855; 51: 12.6855; 52: 12.6855; 1: 12.6855 | 12.6855 | 12.6855 | 12.6855 | 12.6855 | 190282 | 2.9104e-11
Reed | 5165 | RR | LW | RL | DA | 100000 | 11 | 9.0909 | 10 | 10 | [6 empty] | 0 |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 19: x; 20: x; 21: x; 22: x; 23: x; 24: x; 25: x; 26: x; 27: x; 28: x; 29: CC; 30: 1x; 31: 2x; 32: 3x; 33: 4x; 34: CC; 35: 1x; 36: CC; 37: CC; 38: 1x; 39: 2x; 40: 3x; 41: 4x; 42: 5x; 43: 10; 44: 10; 45: 10; 46: 10; 47: 10; 48: 10; 49: 10; 50: 10; 51: 10; 52: 10 |  |  |  |  | 100000 | 0
Keator | 4293 | JC | ASM | MS | DA | 16000 | 4 | 4 | 4 | 4 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 27: x; 28: x; 29: x; 30: x; 31: x; 32: x; 33: x; 34: x; 35: x; 36: CC; 37: CC; 38: 1x; 39: 2x; 40: 3x; 41: 4x; 42: 5x; 43: 4; 44: 4; 45: 4; 46: 4
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14.1149 | 14.1149 | 14.1149 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 23.0824 | 31.3261 | 34.0928 | 48.0462 | 74.8922 | 80.5946 | 80.3912 | 92.0978 | 101.8784 | 93.6548 | 97.5715 | 111.0231 | 111.0231 | 102.554 | 102.554 | 90.054 | 61.1782 | 61.1782 | 61.1782 | 51.3095 | 34.392
Goal of 120K per week. | [20 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [36 empty] | 74.6514 | 100.5363 | 100.5363 | 106.5222 | 107.8274 | 110.1834 | 117.325 | 115.9372 | 119.4372 | 129.4372 | 136.9372 | 117.362 | 104.8081 | 121.1869 | 165.5515 |  | 193.7812 | 194.1979 | 176.802 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 23.0824 | 31.3261 | 34.0928 | 48.0462 | 74.8922 | 80.5946 | 80.3912 | 92.0978 | 101.8784 | 93.6548 | 97.5715 | 116.8565 | 126.1422 | 148.5064 | 157.5064 | 181.054 | 166.4639 | 173.0751 | 181.8251 | 144.623 | 168.3305
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [35 empty] | 70.4212 | 74.6514 | 100.5363 | 100.5363 | 106.5222 | 107.8274 | 110.1834 | 117.325 | 115.9372 | 119.4372 | 129.4372 | 136.9372 | 117.362 | 104.8081 | 121.1869 | 165.5515 | 0 | 179.6663 | 180.083 | 162.6871 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8333 | 15.119 | 45.9524 | 54.9524 | 91 | 105.2857 | 111.8968 | 120.6468 | 93.3135 | 133.9385
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | bar: 49 to 52
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | bar: 20 to 31
Wanke | 4260 | JC | OKM | RL | DA | 35000 | 11 | 3.1818 | 6 | 5.8333 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 24: x; 25: x; 26: x; 27: x; 28: x; 29: CC; 30: x; 31: CC; 32: 1x; 33: 2x; 34: 3x; 35: 4x; 36: CC; 37: CC; 38: 1x; 39: 2x; 40: 3x; 41: 4x; 42: 5x; 43: 5.8333; 44: 5.8333; 45: 5.8333; 46: 5.8333; 47: 5.8333; 48: 5.8333
Uslick | 6111 | JB | LW | JJ | DA | 130000 | 13 | 10 | 14 | 9.2857 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 22: x; 23: x; 24: x; 25: x; 26: x; 27: x; 28: x; 29: x; 30: x; 31: x; 32: x; 33: x; 34: x; 35: CC; 36: 1x; 37: 2x; 38: CC; 39: 1x; 40: 2x; 41: 3x; 42: 4x; 43: 5x; 44: 9.2857; 45: 9.2857; 46: 9.2857; 47: 9.2857; 48: 9.2857; 49: 9.2857; 50: 9.2857; 51: 9.2857; 52: 9.2857; 1: 9.2857 | 9.2857 | 9.2857 | 9.2857 | 9.2857
Valentine | 5084 | RR | LW | RL | DA | 150000 | 10 | 15 | 12 | 12.5 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 37: CC; 38: 1x; 39: CC; 40: 1x; 41: 2x; 42: 3x; 43: 4x; 44: 5x; 45: 12.5; 46: 12.5; 47: 12.5; 48: 12.5; 49: 12.5; 50: 12.5; 51: 12.5; 52: 12.5; 1: 12.5 | 12.5 | 12.5 | 12.5
Jones | 4280 | JC | OKM | JJ | DA | 55000 | 8 | 6.875 | 6 | 9.1667 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 27: x; 28: x; 29: x; 30: x; 31: x; 32: x; 33: x; 34: x; 35: x; 36: x; 37: x; 38: x; 39: CC; 40: 1x; 41: 2x; 42: 3x; 43: 4x; 44: 5x; 45: 9.1667; 46: 9.1667; 47: 9.1667; 48: 9.1667; 49: 9.1667; 50: 9.1667
Shields | 4284 | JC | LW | EI | DA | 55000 | 8 | 6.875 | 6 | 9.1667 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 27: x; 28: x; 29: x; 30: x; 31: x; 32: x; 33: x; 34: x; 35: x; 36: x; 37: x; 38: x; 39: CC; 40: 1x; 41: 2x; 42: 3x; 43: 4x; 44: 5x; 45: 9.1667; 46: 9.1667; 47: 9.1667; 48: 9.1667; 49: 9.1667; 50: 9.1667
Simpson | 4288 | JC | ASM | ?? | DA | 45000 | 10 | 4.5 | 5 | 9 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 40: CC; 41: 1x; 42: 2x; 43: 3x; 44: 4x; 45: 5x; 46: 9; 47: 9; 48: 9; 49: 9; 50: 9
Wierzbicki | 4276 | JC | OKM | RL | DA | 100000 | 10 | 10 | 10 | 10 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 41: CC; 42: 1x; 43: 2x; 44: 3x; 45: 4x; 46: 5x; 47: 10; 48: 10; 49: 10; 50: 10; 51: 10; 52: 10; 1: 10 | 10 | 10 | 10
Harrington | 6133 | JB | OKM | ?? | DA | 50000 | 10 | 5 | 6 | 8.3333 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 37: CC; 38: 1x; 39: 2x; 40: 3x; 41: CC; 42: 1x; 43: 2x; 44: 3x; 45: 4x; 46: 5x; 47: 8.3333; 48: 8.3333; 49: 8.3333; 50: 8.3333; 51: 8.3333; 52: 8.3333
Corey | 6155 | JB | OKM | ?? | DA | 14000 | 10 | 1.4 | 2 | 7 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 37: x; 38: x; 39: x; 40: x; 41: CC; 42: 1x; 43: 2x; 44: 3x; 45: 4x; 46: 5x; 47: 7; 48: 7
Clarke | 5190 | RR | OKM | MF | DA | 150000 | 12 | 12.5 | 14 | 10.7143 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 27: x; 28: x; 29: x; 30: x; 31: x; 32: x; 33: x; 34: x; 35: x; 36: x; 37: x; 38: x; 39: CC; 40: 1x; 41: CC; 42: 1x; 43: 2x; 44: 3x; 45: 4x; 46: 5x; 47: 10.7143; 48: 10.7143; 49: 10.7143; 50: 10.7143; 51: 10.7143; 52: 10.7143; 1: 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143
Stickney | 6140 | JB | OKM | JJ | DA | 200000 | 10 | 20 | 14 | 14.2857 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 42: CC; 43: 1x; 44: 2x; 45: 3x; 46: 4x; 47: 5x; 48: 14.2857; 49: 14.2857; 50: 14.2857; 51: 14.2857; 52: 14.2857; 1: 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857 | 14.2857
Brady | 5179 | RR | LW | RL | DA | 350000 | 12 | 29.1667 | 18 | 19.4444 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 27: x; 28: x; 29: x; 30: x; 31: x; 32: x; 33: x; 34: x; 35: x; 36: x; 37: x; 38: x; 39: CC; 40: 1x; 41: CC; 42: 1x; 43: CC; 44: 1x; 45: 2x; 46: 3x; 47: 4x; 48: 5x; 49: 19.4444; 50: 19.4444; 51: 19.4444; 52: 19.4444; 1: 19.4444 | 19.4444 | 19.4444 | 19.4444 | 19.4444 | 19.4444 | 19.4444 | 19.4444 | 19.4444 | 19.4444 | 19.4444 | 19.4444 | 19.4444 | 19.4444
Kirkey | 4310 | JC | LW | ?? | DA | 75000 | 10 | 7.5 | 8 | 9.375 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 37: x; 38: x; 39: x; 40: x; 41: x; 42: x; 43: CC; 44: x; 45: x; 46: CC; 47: 1x; 48: 2x; 49: 3x; 50: 4x; 51: 5x; 52: 9.375; 1: 9.375 | 9.375 | 9.375 | 9.375 | 9.375 | 9.375 | 9.375
Luthy | 4278 | JC | ASM | MF | DA | 70000 | 8 | 8.75 | 8 | 8.75 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 27: x; 28: x; 29: x; 30: x; 31: x; 32: x; 33: x; 34: x; 35: x; 36: x; 37: x; 38: x; 39: x; 40: CC; 41: x; 42: x; 43: x; 44: CC; 45: 1x; 46: 2x; 47: 3x; 48: 4x; 49: 5x; 50: 8.75; 51: 8.75; 52: 8.75; 1: 8.75 | 8.75 | 8.75 | 8.75 | 8.75
Ball/ Thompson | 5201 | RR | OKM | JJ | DA | 70000 | 10 | 7 | 8 | 8.75 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 43: CC; 44: 1x; 45: CC; 46: 1x; 47: 2x; 48: 3x; 49: 4x; 50: 5x; 51: 6x; 52: 8.75; 1: 8.75 | 8.75 | 8.75 | 8.75 | 8.75 | 8.75 | 8.75
Carpenter | 4302 | JC | OKM | ?? | DA | 175000 | 10 | 17.5 | 14 | 12.5 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 37: x; 38: x; 39: x; 40: x; 41: x; 42: x; 43: x; 44: x; 45: x; 46: CC; 47: 1x; 48: 2x; 49: 3x; 50: 4x; 51: 5x; 52: 12.5; 1: 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5
Hill | 4268 | JC | LW | ?? | DA | 120000 | 10 | 12 | 12 | 10 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 37: x; 38: x; 39: x; 40: x; 41: x; 42: x; 43: x; 44: x; 45: x; 46: CC; 47: 1x; 48: 2x; 49: 3x; 50: 4x; 51: 5x; 52: 10; 1: 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| 5220 | RR | ASM | JJ | DA | 250000 | 10 | 25 | 14 | 17.8571 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 48: CC; 49: 1x; 50: 2x; 51: 3x; 52: 4x; 1: 5x | 17.8571 | 17.8571 | 17.8571 | 17.8571 | 17.8571 | 17.8571 | 17.8571 | 17.8571 | 17.8571 | 17.8571 | 17.8571 | 17.8571 | 17.8571 | 17.8571
Haynes | 5215 | RR | LW | EI | DA | 60000 | 10 | 6 | 8 | 7.5 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 49: CC; 50: 1x; 51: 2x; 52: 3x; 1: 4x | 5x | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Piacentini | 5161 | RR | LW | RL | DA | 550000 | 10 | 55 | 24 | 22.9167 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 21: x; 22: 6.0x; 23: 6.0x; 24: 6.0x; 25: 6.0x; 26: 6.0x; 27: 6.0x; 28: x; 29: x; 30: x; 31: x; 32: CC; 33: 1x; 34: 2x; 35: 3x; 36: 4x; 37: 5x; 38: x; 39: x; 40: x; 41: x; 42: x; 43: x; 44: x; 45: x; 46: x; 47: x; 48: x; 49: CC; 50: 1x; 51: 2x; 52: 3x; 1: 4x | 5x | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167 | 22.9167
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
[23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
[23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
[23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
[23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
[23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | bar: 24
Grant/Haupt (Grandview) |  |  | AM | ?? | DA | 50000 | 10 | 5 | 6 | 8.3333 | [75 empty] | 15: 5.0x; 16: 5.0x; 17: 5.0x; 18: 5.0x; 19: 5.0x; 20: 5.0x; 21: 5.0x; 22: 5.0x; 23: 5.0x; 24: 5.0x; 25: 1x; 26: 2x; 27: 3x; 28: 4x; 29: 5x; 30: 6x; 31: 8.3333; 32: 8.3333; 33: 8.3333; 34: 8.3333; 35: 8.3333; 36: 8.3333
Blanch | 5164 | RR | OM | ?? | DA | 275000 | [14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
[23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | bar: 24
[23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | bar: 24
[23 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
Gatts (UA storm Damage repair) | 5018 | RR | n/a | MS | CLSD | 25348 |  |  | 3 | 8.4493 | n/a | 2017-10-11 | N/A |  | 2 | 2017-11-08 | 10 | 5 | 30 | 2017-12-22 |  | 2018-01-19 |  | 2018-01-19 |  |  | 18 | 10 | 60 | 5 | 15 | 30 | 37.96% | bar: 24
Capital University (Bexley Addition) | 3812 | RR | LW | JC | CLSD | 164803 |  |  | 16 | 10.3002 | 2017-05-02 | 2017-06-16 | 2018-07-11 | 2018-07-17 | 4 | 2017-08-02 | 56 | 3 | 75 | 2017-11-18 |  | 2018-01-08 |  | 2018-01-23 |  |  | 45 | 33 | 150 | 74 | 59 | 75 | 67.11% | bar: 24
Koehler | 3766 | MG | OK | JC | CLSD | 279298 |  |  | 21 | 13.2999 | 2017-02-09 | 2017-05-09 | N/A |  | 5 | 2017-06-20 | 81 | 5 | 95 | 2017-11-03 |  | 2018-01-31 |  | 2018-02-15 |  | 100 | 57 | 40 | 190 | 93 | 86 | 95 | 69.88% | bar: 24
Holzapfel (Cols. Sunroom) | 3870 | RR | AS | JC | CLSD | 58211 |  |  | 10 | 5.8211 | 2017-07-05 | 2017-08-30 | N/A |  | 4 | 2017-09-20 | 45 | 12 | 89 | 2018-01-31 |  | 2018-02-05 |  | 2018-02-15 |  |  | 53.4 | 18 | 178 | 25 | 57 | 89 | 37.27% | bar: 24
Shelton (UA Kitchen/Dormer) | 3774 | MG | AS | RL | CLSD | 163458 |  |  | 16 | 10.2161 | 2017-05-01 | 2017-06-26 | 2017-08-25 | 2017-09-25 | 5 | 2017-10-04 | 63 | 4 | 76 | 2018-01-26 |  | 2018-02-21 |  | 2018-02-21 |  | 100 | 45.6 | 22 | 152 | 188 | 67 | 76 | 86.7% |  | 10.2161 | 10.2161 | 10.2161 | 10.2161 | 10.2161 | 10.2161 | 10.2161
Farrel | 3359 | GC | LW | RL | CLSD | 492000 |  |  | 27 | 18.2222 | 2015-10-21 | 2017-05-19 | N/A |  | 5 | 2017-06-20 | 128 | 12 | 141 | 2018-01-12 |  | 2018-03-08 |  | 2018-03-14 |  | 93 | 84.6 | 51 | 282 | 342 | 140 | 141 | 93.62% |  | 18.2222 | 18.2222 | 18.2222 | 18.2222
Cleary (UA Bath) | 3530 | GC | LW | JC | CLSD | 330000 |  |  | 20 | 16.5 | n/a | 2017-07-01 | 2017-08-13 | 2017-08-23 | 3 | 2017-08-22 | 82 | 20 | 125 | 2018-01-26 |  | 2018-03-01 |  | 2018-04-06 |  |  | 75 | 55 | 250 | 303 | 102 | 125 | 92.04% |  | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5
Hammerle (UA) | 3867 | MG | LW | JJ | CLSD | 154698 |  |  | 20 | 7.7349 | 2017-06-07 | 2017-07-13 | 2017-08-16 | 2017-08-17 | 5 | 2017-08-30 | 77 | 8 | 96 | 2018-01-22 |  | 2018-04-16 |  | 2018-04-16 |  |  | 57.6 | 24 | 192 | 17 | 85 | 96 | 46.35% |  | 7.7349 | 7.7349 | 7.7349 | 7.7349
Northwest Bible (Hilliard, bathroom facelift) | 5045 | RR |  | MS | CLSD | 14888 |  |  | 2 | 7.444 |  | 2018-02-15 | N/A |  | 1 | 2018-04-02 | 12 | 0 | 10 | 2018-04-16 |  | 2018-04-24 |  | 2018-04-27 |  | 100 | 6 | 13 | 20 | 22 | 12 | 10 | 148.9% | [16 empty] | 7.444 | 7.444
Hetterscheidt (North Worthington, master bath) | 4030 | MG | AS | RL | CLSD | 38849 | 16 | 2.4281 | 8 | 4.8561 | 2017-09-27 | 2018-01-11 | 2018-02-03 | 2018-02-27 | 3 | 2018-02-14 | 36 | 0 | 35 | 2018-04-05 |  | 2018-04-16 |  | 2018-05-01 |  | 100 | 21 | 4 | 70 | 67 | 36 | 35 | 72.54% |  | 2.4x | 2.4x | 2.4x | 2.4x | 1x | 2x | 3x | 4x | 4.8561 | 4.8561 | 4.8561 | 4.8561 | 4.8561 | 4.8561 | 4.8561 | 4.8561
Dolch (MBA Deep Run Powell) | 4020 | MG | LW | MF | CLSD | 117286 | 11 | 10.6624 | 11 | 10.6624 | 2017-08-29 | 2017-12-11 | N/A |  | 4 | 2018-01-24 | 46 | 6 | 57 | 2018-04-16 |  | 2018-04-27 |  | 2018-05-02 |  | 100 | 34.2 | 40 | 114 | 92 | 52 | 57 | 96.3% |  | 2x | 3x | 4x | 5x | 6x | 10.6624 | 10.6624 | 10.6624 | 10.6624 | 10.6624 | 10.6624 | 10.6624 | 10.6624 | 10.6624 | 10.6624 | 10.6624
Wongchaowart (Dublin Kit+) | 3873 | RR | OK | JC | CLSD | 229438 |  |  | 18 | 12.7466 | 2017-06-15 | 2017-08-11 | N/A |  | 5 | 2017-10-04 | 63 | 12 | 86 | 2018-02-09 |  | 2018-05-03 |  | 2018-05-03 |  |  | 51.6 | 34 | 172 | 212 | 75 | 86 | 92.12% |  | 12.7466 | 12.7466 | 12.7466 | 12.7466 | 12.7466 | 12.7466 | 12.7466
Linworth Family Dental (Linworth Addition) | 3784 | MG | n/a | RL | CLSD | 246365 | 22 | 11.1984 | 17 | 14.4921 | 2017-03-01 | 2017-08-07 | N/A |  | 5 | 2017-11-20 | 61 | 8 | 109 | 2018-04-27 |  | 2018-05-23 |  | 2018-05-25 |  |  | 65.4 | 27 | 218 | 283 | 69 | 109 | 78.13% |  | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921 | 14.4921
Kumpf (Delaware Kitchen) | 3728 | RR | LW | JJ | CLSD | 169285 |  |  | 22 | 7.6948 | 2017-03-22 | 2017-08-08 | 2017-08-29 | 2017-08-29 | 5 | 2017-08-29 | 93 | 9 | 135 | 2018-03-16 |  | 2018-05-31 |  | 2018-06-05 |  |  | 81 | 48 | 270 | 67 | 102 | 135 | 53.21% |  | 7.6948 | 7.6948 | 7.6948 | 7.6948 | 7.6948 | 7.6948 | 7.6948 | 7.6948 | 7.6948
Jipa (UA Detached Garage) | 3857 | RR | AS | JJ | CLSD | 63935 |  |  | 11 | 5.8123 | 2017-06-08 | 2017-08-01 | N/A |  | 4 | 2017-10-18 | 26 | 0 | 63 | 2018-01-30 |  | 2018-06-01 |  | 2018-06-11 |  |  | 37.8 | 22 | 126 | 17 | 26 | 63 | 37.65% |  | 5.8123 | 5.8123 | 5.8123
Griffith (UA Misc) | 3874 | GC | LW | JJ | CLSD | 208157 | 16 | 13.0098 | 14 | 14.8684 | 2017-06-12 | 2017-09-22 | N/A |  | 4 | 2017-11-08 | 63 | 2 | 82 | 2018-03-12 |  | 2018-07-03 |  | 2018-07-09 | 0 | 100 | 49.2 | 33 | 164 | 115 | 65 | 82 | 72.15% |  | 14.8684 | 14.8684 | 14.8684 | 14.8684 | 14.8684 | 14.8684 | 14.8684 | 14.8684 | 14.8684 | x | x | x | x | x | x | 14.8684 | 14.8684 | x | x | x | 14.8684
Heuerman (UA) | 4008 | MG | OK | JC | CLSD | 85855 |  |  | 10 | 8.5855 | 2017-08-08 | 2017-10-09 | N/A |  | 4 | 2017-12-06 | 55 | 3 | 96 | 2018-04-25 |  | 2018-06-27 |  | 2018-07-13 |  | 100 | 57.6 | 34 | 192 | 164 | 58 | 96 | 68.29% |  | 8.5855 | 8.5855 | 8.5855 | 8.5855 | 8.5855 | 8.5855 | 8.5855 | 8.5855 | 8.5855 | 8.5855 | 8.5855 | 8.5855
Stotts (Kitchen/Master Bath, Lewis Center) | 4031 | MG | OK | JJ | CLSD | 125437 | 17 | 7.3786 | 12 | 10.4531 | 2017-10-27 | 2018-02-22 | N/A |  | 4 | 2018-03-21 | 50 | 5 | 60 | 2018-06-14 |  | 2018-07-20 |  | 2018-07-31 |  | 100 | 36 | 28 | 120 | 130 | 55 | 60 | 92.59% |  | 7.4x | 7.4x | 7.4x | 7.4x | 7.4x | 7.4x | 7.4x | 7.4x | 7.4x | 1x | 2x | 3x | 4x | 10.4531 | 10.4531 | 10.4531 | 10.4531 | 10.4531 | 10.4531 | 10.4531 | 10.4531 | 10.4531 | 10.4531 | 10.4531 | 10.4531
Bavry (April start) ( Porch, Clintonville) | 5012 | RR | AS | RL | CLSD | 48263 | 19 | 2.5402 | 9 | 5.3626 | 2017-10-10 | 2018-02-16 | 2018-04-30 | 2018-04-30 | 2 | 2018-04-02 | 39 | 4 | 44 | 2018-06-04 |  | 2018-08-01 |  | 2018-08-01 |  | 86 | 26.4 | 9 | 88 | 67 | 43 | 44 | 69.32% |  | 2.5x | 2.5x | 2.5x | 2.5x | 2.5x | 2.5x | 2.5x | 2.5x | 2.5x | 1x | 2x | 3x | 4x | 5x | 6x | 5.3626 | 5.3626 | 5.3626 | 5.3626 | 5.3626 | 5.3626 | 5.3626 | 5.3626 | 5.3626
Longberry (Clintonville) | 4034 | MG | AS | JC | CLSD | 100112 | 15 | 6.6741 | 13 | 7.7009 | 2017-10-13 | 2018-01-18 | 2018-02-22 | 2018-02-27 | 4 | 2018-02-21 | 65 | 2 | 69 | 2018-05-30 |  | 2018-06-28 |  | 2018-08-06 | 0 |  | 41.4 | 27 | 138 | 183 | 67 | 69 | 98.31% |  | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 1x | 2x | 3x | 4x |  | 7.7009 | 7.7009 | 7.7009 | 7.7009 | 7.7009 | 7.7009 | 7.7009 | 7.7009 | 7.7009 | 7.7009 | 7.7009 | 7.7009 | 7.7009
Kelley (Exterior refinish, UA) | 4071 | MG | AS | MF | CLSD | 61030 | 10 | 6.103 | 3 | 20.3433 | 2018-02-12 | 2018-04-27 | 2018-06-04 | 2018-06-05 | 2 | 2018-06-06 | 21 | 0 | 15 | 2018-06-27 |  | 2018-07-27 |  | 2018-08-09 |  | 92 | 9 | 2 | 30 | 20 | 21 | 15 | 76.3% | [9 empty] | 5.0x | 5.0x | 5.0x | 5.0x | 5.0x | 5.0x | 5.0x | 5.0x | 5.0x | 5.0x | x | 1x | 2x | 3x | 4x | 5x | 6x | 20.3433 | 20.3433 | 20.3433
Minor (New Albany, Kitchen facelift/office/fireplace) | 3903 | GC | LW | MF | CLSD | 19074 | 5 | 3.8148 | 1 | 19.074 | 2018-04-12 | 2018-05-08 | N/A |  | 1 | 2018-07-16 | 8 |  | 8 | 2018-08-15 |  | 2018-08-30 |  | 2018-08-30 |  |  | 4.8 | 3 | 16 | 44 | 8 | 8 | 145.8% | [14 empty] | 3/23 | D | D | 4.2x | 4.2x | 4.2x | 4.2x | 4.2x | RR out | RR out | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 19.074 | bar: 24
Swift (UA Whole House) | 3866 | GC | AS | RL | CLSD | 381011 | 12 | 31.7509 | 27 | 14.1115 | 2017-04-25 | 2017-08-09 | 2017-08-22 | 2017-08-22 | 5 | 2017-08-28 | 80 | 198 | 241 | 2018-06-01 |  | 2018-09-07 |  | 2018-09-12 |  | 100 | 144.6 | 31 | 482 | 203 | 278 | 241 | 59.64% |  | 14.1115 | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 14.1115 | 14.1115 | 14.1115 | 14.1115 | 14.1115 | 14.1115 | 14.1115 | 14.1115 | 14.1115 | 14.1115 | 14.1115
Nagy (Grove City Screen Porch) | 5023 | RR | AS | JJ | CLSD | 51544 | 25 | 2.0618 | 9 | 5.7271 | 2017-10-25 | 2018-05-07 | N/A |  | 2 | 2018-06-18 | 36 |  | 34 | 2018-08-03 |  | 2018-08-29 |  | 2018-09-12 |  |  | 20.4 | 14 | 68 | 48 | 36 | 34 | 81.7% |  | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | 2.2x | x | x | x | 1x | RR out | RR out | 4x | 5x | 5.7271 | 5.7271 | 5.7271 | 5.7271 | 5.7271 | 5.7271 | 5.7271 | 5.7271 | 5.7271
Bishop Jr (Grandview, bathroom) | 5055 | RR | OK | RL | CLSD | 53648 | 3 | 17.8827 | 9 | 5.9609 |  | 2018-05-11 | N/A |  | 2 | 2018-06-20 | 36 |  | 42 | 2018-08-17 |  | 2018-09-13 |  | 2018-09-13 |  |  | 25.2 | 9 | 84 | 84 | 36 | 42 | 73.81% | [16 empty] | 4/2 | D | D | D | x | 11.7x | RR out | RR out | 3x | 4x | 5x | 5.9609 | 5.9609 | 5.9609 | 5.9609 | 5.9609 | 5.9609 | 5.9609 | 5.9609 | 5.9609 | bar: 24
Boeckman (UA, kitchen facelift) | 3894 | GC | LW | RL | CLSD | 91821 | 9 | 10.2023 | 12 | 7.6517 | 2018-02-23 | 2018-04-27 | N/A |  | 3 | 2018-06-07 | 43 | 10 | 53 | 2018-09-24 |  | 2018-09-13 |  | 2018-09-14 |  |  | 31.8 | 4 | 106 | 111 | 53 | 53 | 72.43% | [6 empty] | D | D | D | D | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | x | 1x | 2x | 3x | 4x | 5x | 7.6517 | 7.6517 | 7.6517 | 7.6517 | 7.6517 | 7.6517 | 7.6517 | 7.6517 | 7.6517 | 7.6517 | 7.6517 | 7.6517 | bar: 24
Pratt/Malik (UA Basement) | 4019 | MG | OK | JJ | CLSD | 223804 | 8 | 27.9755 | 22 | 10.1729 | 2017-09-22 | 2017-11-09 | 2017-12-19 | 2017-12-19 | 4 | 2018-01-10 | 75 | 10 |  | 2018-05-30 |  | 2018-09-05 |  | 2018-10-09 |  | 86 | 0 | 51 | 0 | 73 | 85 | 0 | 0% |  | 6x | 7x | 8x | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | 10.1729 | x | x | x | x | 10.1729 | 10.1729
Yeager (Westerville, Exterior work) | 4092 | MG | OK | MF | CLSD | 72587 | 7 | 10.3696 | 3 | 24.1957 | 2018-04-10 | 2018-05-22 | N/A |  | 3 | 2018-07-30 | 27 |  | 27 | 2018-09-12 |  | 2018-10-01 |  | 2018-10-10 |  | 100 | 16.2 | 14 | 54 | 23 | 27 | 27 | 76.34% | [12 empty] | 3/7 | OK out | OK out | D | D | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 24.1957 | 24.1957 | 24.1957 | bar: 24
Ulman 2017 (Bexley, Patio and Landscaping) | 3802 | MG | OK | RL | CLSD | 118598 | 25 | 4.7439 | 10 | 11.8598 | 2017-09-01 | 2018-04-10 | N/A |  | 4 | 2018-06-13 | 33 |  |  | 2018-08-15 |  | 2018-10-30 |  | 2018-11-09 |  | 100 | 0 | 10 | 0 | 196 | 33 | 0 | 0% |  | 4.7x | 4.7x | 4.7x | 4.7x | 4.7x | x | x | x | x | x | x | x | x | 4.7x | 4.7x | 4.7x | 4.7x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 11.8598 | 11.8598 | 11.8598 | 11.8598 | 11.8598 | 11.8598 | 11.8598 | 11.8598 | 11.8598 | 11.8598
Schwieterman (bathroom /laundry, Clintonville) | 4093 | MG | LW | JJ | CLSD | 50622 | 8 | 6.3277 | 13 | 3.894 | 2018-03-02 | 2018-05-16 | N/A |  | 3 | 2018-06-27 | 41 |  |  | 2018-09-26 |  | 2018-11-13 |  | 2018-11-16 |  | 100 | 0 | 21 | 0 | 80 | 41 | 0 | 0% | [11 empty] | 3/2 | D | D | D | D | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 1x | 2x | 3x | 4x | 5x | 3.894 | 3.894 | 3.894 | 3.894 | 3.894 | 3.894 | 3.894 | 3.894 | 3.894 | 3.894 | 3.894 | 3.894 | 3.894 | bar: 24
Eberle (Hilliard, Wall removal/bar) | 4117 | MG | AS | JJ | CLSD | 55860 | 6 | 9.31 | 12 | 4.655 | 2018-04-26 | 2018-06-06 | N/A |  | 3 | 2018-08-22 | 58 |  |  | 2018-10-12 |  | 2018-11-07 |  | 2018-11-20 |  | 100 | 0 | 16 | 0 | 20 | 58 | 0 | 0% | [19 empty] | 4/26 | 4.3x | 4.3x | 4.3x | 4.3x | 4.3x | 4.3x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 4.655 | 4.655 | 4.655 | 4.655 | 4.655 | 4.655 | 4.655 | 4.655 | 4.655 | 4.655 | 4.655 | 4.655 | bar: 24
Van Tassell (Bathroom, UA) | 4084 | MG | OK | JC | CLSD | 53313 | 8 | 6.6641 | 14 | 3.8081 | 2018-03-27 | 2018-05-24 | N/A |  | 3 | 2018-06-29 | 55 |  |  | 2018-09-25 |  | 2018-11-30 |  | 2018-11-30 |  |  | 0 | 29 | 0 | 91 | 55 | 0 | 0% | [10 empty] | 2/21 | D | D | OK out | OK out | 3.1x | 3.1x | 3.1x | 3.1x | 3.1x | 3.1x | 3.1x | 3.1x | 1x | 2x | 3x | 4x | 5x | 3.8081 | 3.8081 | 3.8081 | 3.8081 | 3.8081 | 3.8081 | 3.8081 | 3.8081 | 3.8081 | 3.8081 | 3.8081 | 3.8081 | 3.8081 | 3.8081 | bar: 24
Mhaskar (Powell Laundry/Mudroom) | 4056 | MG | OK | MF | CLSD | 53873 |  |  | 9 | 5.9859 | 2018-01-12 | 2018-06-04 | N/A |  | 3 | 2018-09-19 | 63 |  | 72 | 2018-11-06 |  | 2018-12-03 |  | 2018-12-03 |  | 100 | 43.2 | 20 | 144 | 45 | 63 | 72 | 55.02% |  | D | D | D | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | x | x | x | x | x | x | x | x | x | x | x | x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 14x | 5.9859 | 5.9859 | 5.9859 | 5.9859 | 5.9859 | 5.9859 | 5.9859 | 5.9859 | 5.9859 | bar: 24
Lawyer (laundry room) | 5073 | RR | LW | JJ | CLSD | 15000 | 5 | 3 | 3 | 5 |  | 2018-08-16 | N/A |  | 3 | 2018-10-09 |  |  |  | 2018-11-02 |  | 2018-11-17 |  | 2018-12-05 |  |  | 0 | 9 | 0 | 33 | 0 | 0 | 0% | [30 empty] | 7/9 | 3x | 3x | 3x | 3x | 3x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 5 | 5 | 5 | 5 | bar: 24
Eikenberry (Kitchen, Bexley) | 4080 | MG | AS | JJ | CLSD | 138770 | 10 | 13.877 | 17 | 8.1629 | 2018-04-13 | 2018-05-25 | 2018-07-06 | 2018-07-24 | 4 | 2018-07-11 | 65 |  |  | 2018-11-07 |  | 2018-11-21 |  | 2018-12-06 |  |  | 0 | 31 | 0 | 67 | 65 | 0 | 0% | [10 empty] | 2/19 | D | D | D | D | D | D | 5.0x | 5.0x | 5.0x | 5.0x | 5.0x | 5.0x | 5.0x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | 8.1629 | bar: 24
Grayem (UA Garage/living room) | 5024 | RR | OK | JC | CLSD | 153308 | 11 | 13.9371 | 24 | 6.3878 | 2017-12-18 | 2018-03-02 | 2018-04-17 | 2018-04-18 | 4 | 2018-04-23 | 76 | 12 | 118 | 2018-10-12 |  | 2018-11-26 |  | 2018-12-07 |  | 100 | 70.8 | 66 | 236 | 108 | 88 | 118 | 71.19% |  | 13.9x | 13.9x | 13.9x | 13.9x | 13.9x | 13.9x | 13.9x | 13.9x | 13.9x | 13.9x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | 6.3878 | bar: 24
Petro/ PB |  | GC |  | T&M | CLSD | 3000 |  |  | 1 | 3 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | bar: 24
Swift | 3333 | GC |  | T&M | CLSD | 3000 |  |  | 1 | 3 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | bar: 24
Mernane (Westerville, leaks) |  | RR |  | JC | CLSD | L&M |  |  | 2 | [15 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [14 empty] | 3 | 3
Bibart (Bexley) | 3879 | GC | AS | MF | CLSD | 96773 | 14 | 6.9124 | 14 | 6.9124 | 2017-07-06 | 2017-10-06 | N/A |  | 4 | 2017-11-15 | 34 | 5 | 38 | 2018-05-14 |  |  | 0 |  | 0 | 100 | 22.8 | 27 | 76 | 23 | 39 | 38 | 83.77% |  | 6.9124 | 6.9124 | 6.9124 | 6.9124 | 6.9124 | 6.9124 | x | x | x | 6.9124 | x | x | x | x | x | 6.9124 | x | x | x | 6.9124
Lee (Grandview Heights Addition) | 4040 | MG | OK | JC | CLSD | 483996 | 15 | 32.2664 | 29 | 16.6895 | 2017-11-16 | 2018-02-28 | N/A |  | 4 | 2018-04-16 | 103 | 6 | 152 | 2018-11-02 |  |  | 0 |  | 0 |  | 91.2 | 84 | 304 | 241 | 109 | 152 | 81.03% |  | 32.3x | 32.3x | 32.3x | 32.3x | 32.3x | 32.3x | 32.3x | 32.3x | 32.3x | 32.3x | 32.3x | 1x | 2x | 3x | 4x | 5x | 6x | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895 | 16.6895
Lane (Kitchen facelift, UA) | 5056 | RR | AS | JJ | CLSD | 58798 | 10 | 5.8798 | 8 | 7.3498 | 2018-04-30 | 2018-06-25 | N/A |  | 2 | 2018-09-12 |  |  |  | 2018-11-30 |  | 2018-12-18 |  |  | 0 | 100 | 0 | 17 | 0 | 31 | 0 | 0 | 0% | [18 empty] | 4/16 | D | 3.5x | 3.5x | RR out | RR out | 3.5x | 3.5x | 3.5x | 3.5x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 14x | 7.3498 | 7.3498 | 7.3498 | 7.3498 | 7.3498 | 7.3498 | 7.3498 | 7.3498 | bar: 24
Abood (Westerville, Master Suite) | 3910 | RR | AS | RL | CLSD | 60000 | 9 | 6.6667 | 8 | 7.5 | 2018-07-12 | 2018-08-27 | N/A |  | 4 | 2018-10-26 | 40 | 40 |  | 2018-12-14 |  |  | 0 |  | 0 | 100 | 0 | 3 | 0 | 70 | 80 | 0 | 0% | [26 empty] | 6/14 | D | D | D | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 |  | 49: 7.5; 50: 7.5; 51: 7.5
Kirkey (UA Sunroom windows) ASAP | 4157 | JS | LW | RL | CLSD | 25000 | 8 | 3.125 | 4 | 6.25 | 2018-08-16 | 2018-10-01 | N/A |  | 3 | 2018-11-08 | 20 | 20 | 42 | 2019-01-11 |  |  | 0 |  | 0 | 100 | 25.2 |  | 84 |  | 40 | 42 | 31.75% | [35 empty] | 3.1x | 3.1x | 3.1x | 3.1x | 3.1x | 3.1x | 3.1x | 3.1x | 1x | 2x | 3x | 4x |  | 6.25 | 6.25 | 6.25 |  | 49: 6.25
Bova (Clintonville Hall Bath/Patio Entrance) | 4032 | MG | AS | MF | CLSD | 158796 | 18 | 8.822 | 17 | 9.3409 | 2018-01-10 | 2018-06-05 | N/A |  | 4 | 2018-08-01 | 55 | 85 |  | 2019-12-20 |  |  | 0 |  | 0 | 100 | 0 |  | 0 |  | 140 | 0 | 0% |  | D | D | D | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | 4.4x | x | x | x | x | x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 9.3409 | 9.3409 | 9.3409 | 9.3409 | 9.3409 | 9.3409 | 9.3409 | 9.3409 | 9.3409 | 9.3409 | 9.3409 | 9.3409 | 9.3409 | 9.3409 |  | 49: 9.3409; 50: 9.3409; 51: 9.3409
Carpenter (Kitchen, UA) | 4091 | MG | OK | RL | CLSD | 295730 | 10 | 29.573 | 17 | 17.3959 | 2018-03-07 | 2018-05-29 | N/A |  | 4 | 2018-08-22 | 85 | 85 | 109 | 2019-01-31 |  |  | 0 |  | 0 | 100 | 65.4 |  | 218 |  | 170 | 109 | 51.99% | [9 empty] | 2/16 | D | D | D | OK out | OK out | 30.0x | 30.0x | 30.0x | 30.0x | 30.0x | 30.0x | 30.0x | 30.0x | 30.0x | 30.0x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 | 17.3959 |  | 49: 17.3959; 50: 17.3959
Chen-Jacinto (Arena District, kitchen facelift) | 3913 | WS | AS | JC | CLSD | 40000 | 7 | 5.7143 | 7 | 5.7143 | 2018-06-26 | 2018-08-17 | N/A |  | 3 | 2018-11-05 | 35 | 35 | 32 | 2019-12-20 |  |  | 0 |  | 0 | 86 | 19.2 |  | 64 |  | 70 | 32 | 72.92% | [27 empty] | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | x | x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 5.7143 | 5.7143 | 5.7143 | 5.7143 |  | 49: 5.7143; 50: 5.7143; 51: 5.7143
Getz (UA bath and office remodel) | 5089 | RR | LW | JJ | CLSD | 35000 | 6 | 5.8333 | 10 | 3.5 | 2018-08-24 | 2018-09-26 | 2018-10-08 | 2018-10-08 | 3 | 2018-10-17 | 50 | 50 | 53 | 2019-01-04 |  |  | 0 |  | 0 | 100 | 31.8 |  | 106 |  | 100 | 53 | 62.89% | [37 empty] | 5.8x | 5.8x | 5.8x | 5.8x | 5.8x | 5.8x |  | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 |  | 49: 3.5; 50: 3.5; 51: 3.5
Ponzani (Olde Towne East Kitchen/Sun Room) | 5034 | RR | LW | RL | CLSD | 174186 | 13 | 13.3989 | 29 | 6.0064 | 2018-01-25 | 2018-05-09 | N/A |  | 4 | 2018-06-27 | 145 | 5 | 151 | 2019-01-31 |  |  | 0 |  | 0 |  | 90.6 |  | 302 |  | 150 | 151 | 33.11% |  |  |  | D | D | D | D | D | D | 13.5x | 13.5x | 13.5x | 13.5x | 13.5x | 13.5x | 13.5x | 13.5x | 13.5x | 13.5x | 13.5x | 13.5x | 1x | RR out | RR out | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 | 6.0064 |  | 49: 6.0064; 50: 6.0064; 51: 6.0064; 52: 6.0064; 1: 6.0064; 2: 6.0064; 3: 6.0064; 4: 6.0064; 5: 6.0064
Stoll (Hilliard Master Suite) | 3891 | GC | OK | JC | CLSD | 112500 | 17 | 6.6176 | 18 | 6.25 | 2017-11-21 | 2018-06-26 | N/A |  | 4 | 2018-09-19 | 90 |  |  | 2019-01-29 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 90 | 0 | 0% |  | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | 10.6x | x | x | x | x | RR out | RR out | x | x | x | x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 |  | 49: 6.25; 50: 6.25; 51: 6.25; 52: 6.25; 1: 6.25; 2: 6.25; 3: 6.25; 4: 6.25
Keefer (UA, bathroom in attic space) | 4133 | MG | LW | MF | CLSD | 60000 | 9 | 6.6667 | 9 | 6.6667 | 2018-07-25 | 2018-10-01 | N/A |  | 5 | 2018-12-12 | 45 |  | 51 | 2019-02-22 |  |  | 0 |  | 0 | 100 | 30.6 |  | 102 |  | 45 | 51 | 29.41% | [25 empty] | 6/4 | D | D | D | D | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 6.7x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x |  | 49: 11x; 50: 6.6667; 51: 6.6667; 52: 6.6667; 1: 6.6667; 2: 6.6667; 3: 6.6667; 4: 6.6667; 5: 6.6667; 6: 6.6667
Harrison (Kichten addition, Clintonville) | 5042 | RR | OK | RL | CLSD | 286019 | 10 | 28.6019 | 22 | 13.0009 | 2018-03-30 | 2018-06-27 | N/A |  | 4 | 2018-09-05 | 110 |  | 119 | 2019-02-28 |  |  | 0 |  | 0 | 100 | 71.4 |  | 238 |  | 110 | 119 | 30.81% | [10 empty] | 2/19 | D | D | OK out | OK out | D | 15.0x | 15.0x | 15.0x | 15.0x | 15.0x | 15.0x | RR out | RR out | 15.0x | 15.0x | 15.0x | x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 13.0009 | 13.0009 | 13.0009 | 13.0009 | 13.0009 | 13.0009 | 13.0009 | 13.0009 | 13.0009 | 13.0009 | 13.0009 |  | 49: 13.0009; 50: 13.0009; 51: 13.0009; 52: 13.0009; 1: 13.0009; 2: 13.0009; 3: 13.0009; 4: 13.0009; 5: 13.0009; 6: 13.0009; 7: 13.0009
Meiling (UA Mstr Ba/ Mudroom) ASAP | 6021 | WS | AS | JJ | CLSD | 150000 | 8 | 18.75 | 14 | 10.7143 | 2018-09-07 | 2018-10-25 |  |  | 5 | 2018-12-03 | 70 |  | 79 | 2019-03-28 |  |  | 0 |  | 0 | 100 | 47.4 |  | 158 |  | 70 | 79 | 29.54% | [38 empty] | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 1x | 2x | 3x | 4x | 10.7143 |  | 49: 10.7143; 50: 10.7143; 51: 10.7143; 52: 10.7143; 1: 10.7143; 2: 10.7143; 3: 10.7143; 4: 10.7143; 5: 10.7143; 6: 10.7143; 7: 10.7143; 8: 10.7143; 9: 10.7143
Glaser (UA, Kitchen and surrounding) | 4107 | MG | LW | MF | CLSD | 225000 | 13 | 17.3077 | 16 | 14.0625 | 2018-05-04 | 2018-09-07 | N/A |  | 5 | 2018-11-28 | 90 |  | 95 | 2019-03-29 |  |  | 0 |  | 0 | 100 | 57 |  | 190 |  | 90 | 95 | 31.58% | [14 empty] | 3/28 | D | D | D | D | D | x | x | x | x | x | 7.7x | 7.7x | 7.7x | 7.7x | 7.7x | 7.7x | 7.7x | 7.7x | 7.7x | 7.7x | 7.7x | 7.7x | 7.7x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 14x | 14.0625 |  | 49: 14.0625; 50: 14.0625; 51: 14.0625; 52: 14.0625; 1: 14.0625; 2: 14.0625; 3: 14.0625; 4: 14.0625; 5: 14.0625; 6: 14.0625; 7: 14.0625; 8: 14.0625; 9: 14.0625; 10: 14.0625; 11: 14.0625
Koehler Updates (Misc/ Concrete and doors) | 4158 | MG | AS | JC | CLSD | 30000 |  |  | 3 | 10 |  | 2018-09-19 | N/A |  | 3 | 2018-10-01 | 30 |  | 44 | 2019-01-04 |  |  | 0 |  |  |  | 26.4 | 18 | 88 | 60 | 30 | 44 | 68.18%
Ozvath (Kitchen, Powell) | 5053 | RR | LW | JJ | CLSD | 90000 | 13 | 6.9231 | 13 | 6.9231 | 2018-05-08 | 2018-08-06 | N/A |  | 4 | 2019-01-04 | 65 |  | 70 | 2019-04-15 |  |  | 0 |  | 0 |  | 42 |  | 140 |  | 65 | 70 | 30.95% | [17 empty] | 4/9 | D | D | D | 6.9x | RR out | RR out | 6.9x | 6.9x | 6.9x | 6.9x | 6.9x | 6.9x | 6.9x | 6.9x | 6.9x | 6.9x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 14x | 15x | 16x | 17x |  | 49: 18x; 50: 19x; 51: 20x; 52: 21x; 1: 6.9231; 2: 6.9231; 3: 6.9231; 4: 6.9231; 5: 6.9231; 6: 6.9231; 7: 6.9231; 8: 6.9231; 9: 6.9231; 10: 6.9231; 11: 6.9231; 12: 6.9231; 13: 6.9231
Anderson | 6034 | JS | AM | JC | CLSD | 40000 | 5 | 8 | 8 | 5 | 2018-11-21 | 2018-12-17 |  |  | 4 | 2019-02-04 | 40 |  |  | 2019-03-28 |  |  | 0 |  | 0 | 100 | 0 |  | 0 |  | 40 | 0 | 0% | [49 empty] | 8.0x | 8.0x |  | 49: 8.0x; 50: 8.0x; 51: 8.0x; 52: 1x; 1: 2x; 2: 3x; 3: 4x; 4: 5x; 5: 6x; 6: 5; 7: 5; 8: 5; 9: 5; 10: 5; 11: 5; 12: 5; 13: 5
Mhaskar | 4056 | MG | OK | MF | CLSD | 7301.25 |  |  | 8 | 0.91266 | ? |  |  |  |  | 2018-09-02 | 40 |  | 40 | bar: 14 to 15
Ferris (C-Ville Kit and Ba) ?? | 6008 | JS | AS | JC | CLSD | 165000 | 12 | 13.75 | 16 | 10.3125 | 2018-08-16 | 2018-11-01 |  |  | 5 | 2019-01-04 | 80 |  | 70 | 2019-04-15 |  |  | 0 |  | 0 |  | 42 |  | 140 |  | 80 | 70 | 38.1% | [35 empty] | 17.9x | 17.9x | 17.9x | 17.9x | 17.9x | 17.9x | 17.9x | 17.9x | 17.9x | 17.9x | 17.9x | 17.9x | 1x | 2x | 3x | 4x |  | 49: 5x; 50: 6x; 51: 7x; 52: 10.3125; 1: 10.3125; 2: 10.3125; 3: 10.3125; 4: 10.3125; 5: 10.3125; 6: 10.3125; 7: 10.3125; 8: 10.3125; 9: 10.3125; 10: 10.3125; 11: 10.3125; 12: 10.3125; 13: 10.3125; 14: 10.3125; 15: 10.3125
Oldham (UA, kitchen, bathroom, exterior) | 4119 | MG | LW | RL | CLSD | 120000 | 10 | 12 | 13 | 9.2308 | 2018-05-24 | 2018-08-08 | N/A |  | 5 | 2019-01-04 | 65 |  | 78 | 2019-04-25 |  |  | 0 |  | 0 | 7 | 46.8 |  | 156 |  | 65 | 78 | 27.78% | [19 empty] | 4/19 | D | D | D | D | 12.0x | 12.0x | 12.0x | 12.0x | 12.0x | 12.0x | 12.0x | 12.0x | 12.0x | 12.0x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 14x | 15x | 16x | 17x | 18x | 19x |  | 49: 20x; 50: 21x; 51: 22x; 52: 23x; 3: 9.2308; 4: 9.2308; 5: 9.2308; 6: 9.2308; 7: 9.2308; 8: 9.2308; 9: 9.2308; 10: 9.2308; 11: 9.2308; 12: 9.2308; 13: 9.2308; 14: 9.2308; 15: 9.2308
Hornback | 6060 | JS | AM | MF | CLSD | 25000 | 8 | 3.125 | 3 | 8.3333 | 2018-12-11 |  |  |  |  | 2019-04-02 | 15 | 1 | 16 | 2019-04-09 |  |  | 0 |  | 0 |  | 9.6 |  | 32 |  | 16 | 16 | 33.33% | [52 empty] | 50: DA; 51: DA; 52: DA; 1: DA; 2: DA; 3: DA; 4: DA; 5: DA; 6: 1x; 7: 2x; 8: 3x; 9: 4x; 10: 5x; 11: 6x; 12: 7x; 13: 8x; 14: 8.3333; 15: 8.3333; 16: 8.3333
Maheras/Francis (UA office) ASAP | 5091 | RR | LW | JJ | CLSD | 60000 | 17 | 3.5294 | 9 | 6.6667 | 2018-08-22 | 2018-12-11 |  |  | 3 | 2019-02-04 | 45 |  | 58 | 2019-04-25 |  |  | 0 |  | 0 |  | 34.8 |  | 116 |  | 45 | 58 | 0.25862 | [36 empty] | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 49: 3.5x; 50: 2x; 51: 3x; 52: 4x; 1: 5x; 2: 6x; 3: 7x; 4: 8x; 5: 9x; 6: 10x; 7: 11x; 8: 6.6667; 9: 6.6667; 10: 6.6667; 11: 6.6667; 12: 6.6667; 13: 6.6667; 14: 6.6667; 15: 6.6667; 16: 6.6667
Cook/Durae (UA Kitchen) ASAP | 5096 | RR | LW | RL | CLSD | 123264 | 14 | 8.8046 | 14 | 8.8046 | 2018-09-19 | 2018-12-20 | N/A | N/A | 4 | 2019-02-06 | 70 |  | 64 | 2019-05-17 |  | 2019-06-05 |  |  | 0 |  | 38.4 |  | 128 |  | 70 | 64 | 36.46% | [40 empty] | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 8.8x | 49: 8.8x; 50: 8.8x; 51: 4x; 52: 5x; 1: 6x; 2: 7x; 3: 8x; 4: 9x; 5: 10x; 6: 11x; 7: 8.8046; 8: 8.8046; 9: 8.8046; 10: 8.8046; 11: 8.8046; 12: 8.8046; 13: 8.8046; 14: 8.8046; 15: 8.8046; 16: 8.8046; 17: 8.8046; 18: 8.8046; 19: 8.8046; 20: 8.8046
Grayem 2 (C-Ville) | 5111 | RR | OK | MF | CLSD | 171340 | 13 | 13.18 | 12 | 14.2783 | 2018-11-07 | 2019-02-01 | N/A | N/A | 5 | 2019-03-13 | 60 |  | 71 | 2019-06-20 |  | 2019-06-24 |  |  | 0 |  | 42.6 |  | 142 |  | 60 | 71 | 28.17% | [47 empty] | 7.7x | 7.7x | 7.7x | 7.7x | 7.7x | 49: 7.7x; 50: 7.7x; 51: 7.7x; 52: 7.7x; 1: 7.7x; 2: 7.7x; 3: 7.7x; 4: 7.7x; 5: 1x; 6: 2x; 7: 3x; 8: 4x; 9: 5x; 10: 14.2783; 11: 14.2783; 12: 14.2783; 13: 14.2783; 14: 14.2783; 15: 14.2783; 16: 14.2783; 17: 14.2783; 18: 14.2783; 19: 14.2783; 20: 14.2783; 21: 14.2783
McClintock (Riverlea Porch and Roof) Spring | 5075 | RR | LW | JJ | CLSD | 60533 | 10 | 6.0533 | 6 | 10.0888 | 2018-08-03 | 2018-12-20 | N/A | N/A | 3 | 2019-04-09 | 30 |  | 24 | 2019-05-10 |  | 2019-06-04 |  | 2019-05-10 |  |  | 14.4 |  | 48 |  | 30 | 24 | 41.67% | [33 empty] | 4.0x | 4.0x | 4.0x | 4.0x | 4.0x | 4.0x | 4.0x | 4.0x | 4.0x | 4.0x | 4.0x | 4.0x | 1x | 2x | 3x | 4x | 5x | 6x |  | 49: 7x; 50: 8x; 51: 9x; 52: 10x; 1: 11x; 2: 12x; 3: 13x; 4: 14x; 5: 15x; 6: 16x; 7: 17x; 8: 18x; 9: 19x; 14: 10.0888; 15: 10.0888; 16: 10.0888; 17: 10.0888; 18: 10.0888; 19: 10.0888
Getz (Brick Wall) | 5166 | RR |  | JJ | CLSD | 5732 | 1 | 5.732 | 1 | 5.732 |  |  | N/A | N/A | 1 | 2019-06-10 | 5 |  | 4 | 2019-06-14 |  |  | 0 |  | 0 |  | 2.4 |  | 8 |  | 5 | 4 | 41.67% | [52 empty] | 19: 1x; 20: 2x; 21: 3x; 22: 4x; 23: 5.732; 24: 5.732
Reichley (Bexley) | 5106 | RR | OKM | EI | CLSD | 78579 | 13 | 6.0445 | 10 | 7.8579 | 2018-11-27 | 2019-03-20 | N/A | N/A | 4 | 2019-05-08 | 50 |  | 49 | 2019-07-17 |  | 2019-07-10 |  |  | 0 |  | 29.4 |  | 98 |  | 50 | 49 | 34.01% | [50 empty] | 10x |  | 49: 10x; 50: 10x; 51: 10x; 52: 10x; 1: 10x; 2: 10x; 3: 10x; 4: 10x; 5: 10x; 6: 10x; 7: 10x; 8: 10x; 9: 10x; 10: 10x; 11: 10x; 12: 1x; 13: 2x; 14: 3x; 15: 4x; 16: 5x; 17: 6x; 18: 7.8579; 19: 7.8579; 20: 7.8579; 21: 7.8579; 22: 7.8579; 23: 7.8579; 24: 7.8579; 25: 7.8579; 26: 7.8579; 27: 7.8579
Sommers (Dublin KIT) | 4193 | JS | OKM | MF | CLSD | 31250 | 8 | 3.9062 | 7 | 4.4643 |  | 2019-04-05 |  |  | 3 | 2019-05-09 | 35 |  | 36 | 2019-07-10 |  |  | 0 |  | 0 |  | 21.6 |  | 72 |  | 35 | 36 | 32.41% | [52 empty] | 5: x; 6: x; 7: x; 8: x; 9: x; 10: x; 11: x; 12: x; 13: x; 14: 1x; 15: 2x; 16: 3x; 17: 4x; 18: 4.4643; 19: 4.4643; 20: 4.4643; 21: 4.4643; 22: 4.4643; 23: 4.4643; 24: 4.4643; 25: 4.4643; 26: 4.4643; 27: 4.4643
Rahl (Powell, addition kitchen/dining/laundry) | 5071 | RR | LW | RL | CLSD | 324642 | 8 | 40.5802 | 23 | 14.1149 | 2018-07-16 | 2018-11-30 | N/A | N/A | 5 | 2018-12-19 | 115 |  | 108 | 2019-05-24 |  | 2019-06-06 |  |  | 0 |  | 64.8 |  | 216 |  | 115 | 108 | 35.49% | [26 empty] | 6/14 | D | D | D | D | 37.5x | 37.5x | 37.5x | 37.5x | 37.5x | 37.5x | 37.5x | 37.5x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x |  | 49: 14.1149; 50: 14.1149; 51: 14.1149; 52: 14.1149; 1: 14.1149; 2: 14.1149; 3: 14.1149; 4: 14.1149; 5: 14.1149; 6: 14.1149; 7: 14.1149; 8: 14.1149; 9: 14.1149; 10: 14.1149; 11: 14.1149; 12: 14.1149; 13: 14.1149; 14: 14.1149; 15: 14.1149; 16: 14.1149; 17: 14.1149; 18: 14.1149; 19: 14.1149; 20: 14.1149; 21: 14.1149; 22: 14.1149; 23: 14.1149 |  |  |  |  | 381101.4783 | -56459.4783
Marshall (Hoover Res Garage Addition) ASAP | 5077 | RR | LW | JJ | CLSD | 240709 | 18 | 13.3727 | 13 | 18.5161 | 2018-10-31 | 2019-03-05 | N/A | N/A | 5 | 2019-05-13 | 65 |  | 63 | 2019-08-09 |  | 2019-08-19 |  |  | 0 |  | 37.8 |  | 126 |  | 65 | 63 | 34.39% | [46 empty] | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 9.7x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 18.5161 | 18.5161 | 18.5161 | 18.5161 | 18.5161 | 18.5161 | 18.5161 | 18.5161 | 18.5161 | 18.5161 | 18.5161 | 18.5161 | 18.5161 | [26 empty] | 240709 | 0
Manion (C-Ville FP) | 6046 | JS | ASM | MF | CLSD | 18774 | 12 | 1.5645 | 10 | 1.8774 | 2018-12-20 | 2019-04-17 |  |  | 3 | 2019-06-05 | 50 |  | 42 | 2019-08-02 |  | 2019-08-29 |  |  | 0 |  | 25.2 |  | 84 |  | 50 | 42 | 39.68% | [52 empty] | 50: 1.3x; 51: 1.3x; 52: 1.3x; 1: 1.3x; 2: 1.3x; 3: 1.3x; 4: 1.3x; 5: 1.3x; 6: 1.3x; 7: 1.3x; 8: 1.3x; 9: 1.3x; 10: 1.3x; 11: 1.3x; 12: 1.3x; 13: 1.3x; 14: 1.3x; 15: 1.3x; 16: 1x; 17: 2x; 18: 3x; 19: 4x; 20: 5x; 21: 6x; 22: 1.8774; 23: 1.8774; 24: 1.8774; 25: 1.8774; 26: 1.8774; 27: 1.8774; 28: 1.8774; 29: 1.8774; 30: 1.8774; 31: 1.8774 |  |  |  |  | 18774 | 0
Block (Westerville) | 5138 | RR | ASM | JJ | CLSD | 58547 | 8 | 7.3184 | 6 | 9.7578 | 2019-03-20 | 2019-05-22 |  |  | 3 | 2019-07-17 | 30 |  | 18 | 2019-08-09 |  | 2019-08-27 |  |  | 0 | 93 | 10.8 |  | 36 |  | 30 | 18 | 55.56% | [52 empty] | 11: 6x; 12: 6x; 13: 6x; 14: 6x; 15: 6x; 16: 6x; 17: 6x; 18: 6x; 19: 6x; 20: 6x; 21: 1x; 22: 2x; 23: 3x; 24: 4x; 25: 5x; 26: 6x; 27: 7x; 28: 9.7578; 29: 9.7578; 30: 9.7578; 31: 9.7578; 32: 9.7578; 33: 9.7578 |  |  |  |  | 58547 | 7.276e-12
Smith | 5125 | RR | LW | RL | CLSD | 56550 | 13 | 4.35 | 8 | 7.0687 | 2019-02-14 | 2019-05-09 | N/A | N/A | 3 | 2019-07-08 | 40 |  | 24 | 2019-08-08 |  | 2019-08-30 |  |  | 2019-08-30 |  | 14.4 |  | 48 |  | 40 | 24 | 55.56% | [52 empty] | 6: 6.9x; 7: 6.9x; 8: 6.9x; 9: 6.9x; 10: 6.9x; 11: 6.9x; 12: 6.9x; 13: 6.9x; 14: 6.9x; 15: 6.9x; 16: 6.9x; 17: 6.9x; 18: 6.9x; 19: 1x; 20: 2x; 21: 3x; 22: 4x; 23: 5x; 24: 6x; 25: 7x; 26: 8x; 27: 7.0687; 28: 7.0687; 29: 7.0687; 30: 7.0687; 31: 7.0687; 32: 7.0687; 33: 7.0687; 34: 7.0687 |  |  |  |  | 56550 | -7.276e-12
Crum (Northwest Columbus) | 6129 | JB |  | MS | CLSD | 17634 | 0 | 0 | 4 | 4.4085 |  | 2019-07-25 | N/A | N/A | 1 | 2019-08-14 | 20 |  | 24 | 2019-09-02 |  | 2019-09-06 |  |  | 0 |  | 14.4 |  | 48 |  | 20 | 24 | 27.78% | [52 empty] | 29: CC; 30: 2x; 31: 3x; 32: 4.4085; 33: 4.4085; 34: 4.4085; 35: 4.4085 |  |  |  |  | 17634 | 0
Bellaire (UA Kit, Mstr Ba, misc) ASAP | 5078 | RR | LW | RL | CLSD | 246992 | 25 | 9.8797 | 17 | 14.5289 | 2018-10-23 | 2019-04-12 | N/A | N/A | 5 | 2019-05-14 | 85 |  |  | 2019-09-24 |  | 2019-10-01 |  |  | 0 |  | 0 |  | 0 |  | 85 | 0 | 0% | [39 empty] | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 8x | 1x | 2x | 3x | 4x | 5x | 6x | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | 14.5289 | [20 empty] | 246992 | -5.8208e-11
DeGirolamo/Weldon (C-Ville) | 4236 | JS | ASM | RL | CLSD | 54104 | 10 | 5.4104 | 9 | 6.0116 | 2019-03-20 | 2019-05-22 |  |  | 3 | 2019-07-17 | 45 |  |  | 2019-09-18 |  | 2019-09-26 |  |  | 0 |  | 0 |  | 0 |  | 45 | 0 | 0% | [52 empty] | 11: 5.4x; 12: 5.4x; 13: 5.4x; 14: 5.4x; 15: 5.4x; 16: 5.4x; 17: 5.4x; 18: 5.4x; 19: 5.4x; 20: 5.4x; 21: 1x; 22: 2x; 23: 3x; 24: 4x; 25: 5x; 26: 6x; 27: 7x; 28: 6.0116; 29: 6.0116; 30: 6.0116; 31: 6.0116; 32: 6.0116; 33: 6.0116; 34: 6.0116; 35: 6.0116; 36: 6.0116 |  |  |  |  | 54104 | 7.276e-12
Passino (C-Ville) | 3930 | JC | ASM | EI | CLSD | 77939 | 8 | 9.7424 | 9 | 8.6599 | 2019-03-27 | 2019-05-31 |  |  | 5 | 2019-07-22 | 45 |  |  | 2019-09-13 |  | 2019-09-13 |  |  | 0 |  | 0 |  | 0 |  | 45 | 0 | 0% | [52 empty] | 14: 8.8x; 15: 8.8x; 16: 8.8x; 17: 8.8x; 18: 8.8x; 19: 8.8x; 20: 8.8x; 21: 8.8x; 22: 1x; 23: 2x; 24: 3x; 25: 4x; 26: 5x; 27: 6x; 28: 7x; 29: 8.6599; 30: 8.6599; 31: 8.6599; 32: 8.6599; 33: 8.6599; 34: 8.6599; 35: 8.6599; 36: 8.6599; 37: 8.6599 |  |  |  |  | 77939 | 0
MacDonald/Fisher (UA) | 3937 | JB | ASM | MF | CLSD | 25323 | 7 | 3.6176 | 1 | 25.323 |  | 2019-05-20 |  |  | 2 | 2019-08-22 | 5 |  |  | 2019-08-27 |  | 2019-08-27 |  |  | 0 |  | 0 |  | 0 |  | 5 | 0 | 0% | [52 empty] | 12: 5.0x; 13: 5.0x; 14: 5.0x; 15: 5.0x; 16: 5.0x; 17: 5.0x; 18: 5.0x; 19: 1x; 20: 2x; 21: 3x; 22: 4x; 23: 5x; 24: 6x; 25: 7x; 26: 8x; 27: 9x; 28: 10x; 29: 11x; 30: 12x; 31: 13x; 32: 14x; 33: 25.323 |  |  |  |  | 25323 | 0
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0% | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0625 |  | 14.0625 | 14.0625 | 14.0625 |  | 31.3504 | 31.3504 | 40.5812 | 40.5812 | 40.5812 | 45.5812 | 54.3858 | 61.0525 | 61.0525 | 75.3308 | 75.3308 | 75.3308 | 75.3308 | 81.8299 | 81.8299 | 62.2866 | 47.2866 | 59.6088 | 78.1249 | 68.036 | 73.7604 | 61.3595 | 67.0915 | 52.9766 | 47.2446 | 47.2446 | 54.3134 | 57.7606 | 66.4204 | 66.4204 | 66.4204 | 50.4355 | 75.7585 | 40.6776 | 33.6089 | 29.2004 | 23.1888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 0 | 0 | 0%
Reese | 3603 | GC | LW |  | LOST | 650000 |  |  | 24 | 27.0833 | 2016-05-20 | [19 empty] | 0 | 0 | 0% | bar: 24
Kentner | 3621 | MG | CB |  | LOST | 125000 |  |  | 15 | 8.3333 | 2017-08-11 | [19 empty] | 0 | 0 | 0% | bar: 24
Boster 2 | 3560 | MG | LW |  | LOST | 90000 |  |  | 11 | 8.1818 | [20 empty] | 0 | 0 | 0% | bar: 24
Fronk | 3543 | GC | CB |  | LOST | 475000 |  |  | 22 | 21.5909 | 2016-08-02 | [19 empty] | 0 | 0 | 0% | bar: 24
Nichols | 3680 | RR | LW |  | LOST | 50000 |  |  | 11 | 4.5455 | 2016-10-10 | [19 empty] | 0 | 0 | 0% | bar: 24
Rusin | 3623 | MG | OK |  | LOST | 90000 |  |  | 10 | 9 | 2016-07-21 | [19 empty] | 0 | 0 | 0% | bar: 24
Garman | 3558 | MG | OK |  | LOST | 50000 |  |  | 8 | 6.25 | 2016-08-22 | [19 empty] | 0 | 0 | 0% | bar: 24
McEllistream | 3695 | RR | OK |  | LOST | 30000 |  |  | 6 | 5 | 2016-11-11 | [19 empty] | 0 | 0 | 0% | bar: 24
College/Bowen | 3716 | MG | LW |  | LOST | 80000 |  |  | 10 | 8 | 2017-01-31 | [19 empty] | 0 | 0 | 0% | bar: 24
Drake_Martyn | 3771 | RR | LW |  | LOST | 150000 |  |  | 14 | 10.7143 | 2017-01-19 | [19 empty] | 0 | 0 | 0% | bar: 24
Weiler | 3846 | MG |  |  | LOST | 15000 |  |  | 2 | 7.5 | [20 empty] | 0 | 0 | 0% | bar: 24
McCabe | 3742 | MG | LW |  | LOST | 60000 |  |  | 9 | 6.6667 | 2017-01-19 | [19 empty] | 0 | 0 | 0% | bar: 24
Gummer (UA Bath) | 3586 | GC | AS |  | LOST | 60000 |  |  | 9 | 6.6667 | 2017-04-27 | [19 empty] | 0 | 0 | 0% | bar: 24
Lyon (Gahanna Addition) | 3850 | RR | OK |  | LOST | 60000 |  |  | 8 | 7.5 | 2017-05-18 | [19 empty] | 0 | 0 | 0% | bar: 24
Converse '17 (UA Addition) | 3807 | MG | LW |  | LOST | 230000 |  |  | 16 | 14.375 | 2017-02-03 | [19 empty] | 0 | 0 | 0% | bar: 24
Smith | 3681 | RR | OK |  | LOST | 300000 |  |  | 10 | 30 | [20 empty] | 0 | 0 | 0% |  | x | x | x | bar: 24
Blissmer | 3782 | RR | OK |  | LOST | 200000 |  |  | 8 | 25 | [20 empty] | 0 | 0 | 0% | bar: 24
Gould | 3815 | MG |  |  | LOST | 400000 |  |  | 12 | 33.3333 | [20 empty] | 0 | 0 | 0% |  | x | x | x | x | x | x | x | x | x | x | x | bar: 24
Lagusch | 5001 | RR | AS |  | LOST | 150000 |  |  | 12 | 12.5 | [20 empty] | 0 | 0 | 0% |  | x | x | x | x | x | x | x | x | bar: 24
Keenan (Dublin MBA) | 4037 | MG | OK |  | LOST | 60000 |  |  | 9 | 6.6667 | 2017-10-30 | [19 empty] | 0 | 0 | 0% | bar: 24
Dutton (UA Master Bath/Kitchen) | 5022 | RR | OK |  | LOST | 180000 |  |  | 12 | 15 | [20 empty] | 0 | 0 | 0% |  | 18.0x | 18.0x | 18.0x | 18.0x | 18.0x | 18.0x | 18.0x | bar: 24
Hansen (Living Room, UA) | 4094 | MG | AS |  | LOST | 20000 |  |  | 5 | 4 | [20 empty] | 0 | 0 | 0% | bar: 24
Boster 2 (MBA Clintonville) | 3560 | MG | LW | JJ | LOST | 90000 |  |  | 10 | 9 | 2017-06-24 | [19 empty] | 0 | 0 | 0% |  | 6.4x | 6.4x | 6.4x | 6.4x |  |  | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | bar: 24
Plum (UA, shower) | 5054 | RR | LW |  | LOST | 15000 | 6 | 2.5 | 6 | 2.5 | [20 empty] | 0 | 0 | 0% | [14 empty] | 3/21 | D | D | D | D | 2.5x | 2.5x | 2.5x | RR out | RR out | 2.5x | bar: 24
Saylor/Ringor (South Campus, Screen Porch) | 4125 | MG | OK |  | LOST | 80000 |  |  | 9 | 8.8889 | [20 empty] | 0 | 0 | 0% | bar: 24
Roberts (Worthington Hills, Master Bath) | 4108 | MG | OK |  | LOST | 100000 | 10 | 10 | 8 | 12.5 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [18 empty] | 4/18 | D | D | x | x | x | x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | bar: 24
Susi (Addition, Dublin) | 4104 | MG | OK | RL | LOST | 180000 | 6 | 30 | 16 | 11.25 | 2018-04-27 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [16 empty] | 4/2 | D | D | D | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | bar: 49 to 52; 24
Ramakrishnan (Westerville, Living Room Addition) | 5029 | RR | LW |  | LOST | 200000 | 12 | 16.6667 | 16 | 12.5 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [24 empty] | 6/1 | D | D | D | D | D | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | 16.7x | bar: 24
Hoffman (Linworth, Kitchen) | 4127 | MG | OK |  | LOST | 100000 | 8 | 12.5 | 12 | 8.3333 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [24 empty] | 5/30 | D | D | D | 12.5x | 12.5x | 12.5x | 12.5x | 12.5x | 12.5x | 12.5x | 12.5x | bar: 24
Hazzard (Inlaw suite Knolls) | 5081 | RR | LW | JC | LOST | 85000 |  |  | 11 | 7.7273 | [20 empty] | 0 | 0 | 0% | bar: 49 to 6; 24
Melillo | 6042 | JS | AM | ?? | LOST | 40000 | 12 | 3.3333 | 4 | 10 | 2018-11-08 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [47 empty] | 3.3x | 3.3x | 3.3x | 3.3x |  | 49: 3.3x; 50: 3.3x; 51: 3.3x; 52: 3.3x; 1: 3.3x; 2: 3.3x; 3: 3.3x; 4: 3.3x; 5: 1x; 6: 2x; 7: 3x; 8: 4x; 9: 5x; 10: 6x; 12: 10; 13: 10; 14: 10; 15: 10
[31 empty] | 0 | 0 | 0% | bar: 49 to 6; 24
Rost (Clintonville Guest Bath/Laundry) | 3715 | RR | OK | MF | ICU | 50000 |  |  | 9 | 5.5556 | 2016-11-18 | [19 empty] | 0 | 0 | 0% |  | x | x | x | x | x | bar: 24
Blum (Dublin Kit) | 5007 | RR | LW |  | ICU | 100000 |  |  | 8 | 12.5 | bar: 24
Gable | 4021 | MG | LW |  | ICU | bar: 24
Geraghty (Kit Linworth) | 3667 | GC | AS |  | ICU | 90000 |  |  | 9 | 10 | 2017-06-27 | [23 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | bar: 24
Scott (Clintonville) | 4045 | MG | AS | JJ | ICU | 150000 |  |  | 10 | 15 | [24 empty] | 15.0x | 15.0x | 15.0x | 15.0x | 15.0x | 15.0x | 15.0x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x
Ramakrishnan (Galena Porch/Patio/Landscape) | 5029 | RR | LW | RL | ICU | 200000 |  |  | 14 | 14.2857 | [24 empty] | D | D | 20.0x | 20.0x | 20.0x | 20.0x | 20.0x | 20.0x | 20.0x | 20.0x | 20.0x | 20.0x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 14x | 15x | bar: 24
Sparks (Westerville) | 4046 | MG | LW | JC | ICU | 40000 |  |  | 8 | 5 | [29 empty] | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | 5.7x | bar: 24
Cordle (Dublin Bathroom plus) | 3888 | GC | AS | JJ | ICU | 100000 |  |  | 10 | 10 | [29 empty] | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | bar: 24
Babner ( Muirfield Outdoor Living Space) | 4027 | MG | LW | JC | ICU | 300000 |  |  | 14 | 21.4286 | 2017-08-30 | [23 empty] | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 10.0x | 2x
ICU | bar: 24
Hague (Ashville) | 4015 | MG | LW | RL | ICU | 380000 |  |  | 24 | 15.8333 | 2017-08-22 | [23 empty] | 17.3x | 17.3x | 17.3x | 17.3x | 17.3x | 17.3x | 17.3x | 17.3x | 17.3x | 17.3x | 17.3x | 1x | 2x | 3x | 4x | 5x | 6x | 7x
Kuhl (May start) (Worthington) | 3573 | GC | LW |  | ICU | 330000 |  |  | 18 | 18.3333 | 2017-03-07 | [23 empty] | x | x | x | x | x | x | x | x | x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x
Boster 2 (MBA Clintonville) | 3560 | MG | LW | JJ | ICU | 90000 |  |  | 10 | 9 | 2017-06-24 | [23 empty] | 6.4x | 6.4x | 6.4x | 6.4x |  |  | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 6.4x | 1x | 2x | 3x | bar: 24
O'Leary (Hilliard) | 5010 | RR | LW | RL | ICU | 170000 |  |  | 12 | 14.1667 | 2017-10-16 | [23 empty] | 14.2x | 14.2x | 14.2x | 14.2x | x | x | x | x | x | x | x | x | x | x | x | x | 3x | 4x
Verner (Delaware Master Bath) | 5026 | RR | AS | JJ | ICU | 50000 | 11 | 4.5455 | 9 | 5.5556 | 2018-01-05 | [25 empty] | 4.5x | 4.5x | 4.5x | 4.5x | 4.5x | 4.5x | 4.5x | 4.5x | 4.5x | 4.5x | 4.5x | x | x | x | x | x | x | 1x | 2x | 3x | 4x | 5x | bar: 24
Rothe (Kitchen, UA) | 5043 | RR | LW | RL | ICU | 110000 | 11 | 10 | 12 | 9.1667 | 2018-02-22 | [28 empty] | D | D | D | D | 9.1x | 9.1x | 9.1x | 9.1x | 9.1x | 9.1x | 9.1x | 9.1x | 9.1x | 9.1x | 9.1x | 1x | RR out | RR out | 4x | bar: 24
Hanson 2018 (Powell, Pantry) | 4094 | MG | AS |  | ICU | 25000 | 5 | 5 | 8 | 3.125 | [37 empty] | 3/21 | D | D | D | D | 5.0x | 5.0x | 5.0x | 5.0x | 5.0x | bar: 24
Weeks (Clintonville, Addition) | 4121 | MG | OK |  | ICU | 100000 |  |  | 16 | 6.25 | bar: 24
Armstrong (Westerville, kitchen and surrounding) | 4116 | MG | LW |  | ICU | 200000 | 15 | 13.3333 | 12 | 16.6667 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [18 empty] | 4/19 | D | D | D | x | x | x | x | x | x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | 13.3x | bar: 24
Hevezi (Arlington living addition, laundry, bathroom) | 5039 | RR | OK | RL | ICU | 250000 | 21 | 11.9048 | 20 | 12.5 | 2018-02-13 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [5 empty] | D | D | D | D | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | RR out | RR out | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | 8.3x | x | x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 |  | 49: 12.5; 50: 12.5; 51: 12.5; 52: 12.5; 1: 12.5; 2: 12.5; 3: 12.5; 4: 12.5; 5: 12.5
Geraghty (Kit Linworth) | 3667 | GC | AS | JC | ICU | 90000 | 18 | 5 | 9 | 10 | 2017-06-27 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 10 | 10 | 10 | 10 | 10 | 10 |  | 49: 10; 50: 10; 51: 10; 52: 10
Palmer (Dublin Master Bath) | 4047 | MG | LW | JC | ICU | 163788 | 12 | 13.649 | 10 | 16.3788 | 2018-01-06 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% |  | D |  |  |  |  | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | 18.8x | x | x | x | x | x | F | F | F | F | F | F | F | F | F | F | F | F | F | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | 11x | 12x | 13x | 16.3788 | 16.3788 |  | 49: 16.3788; 50: 16.3788; 51: 16.3788; 52: 16.3788; 1: 16.3788; 2: 16.3788; 3: 16.3788; 4: 16.3788
Baumbusch (UA, exterior living space) | 3915 | WS | AS | JC | ICU | 18000 | 6 | 3 | 5 | 3.6 | 2018-06-20 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [27 empty] | 3.0x | 3.0x | 3.0x | 3.0x | 3.0x | 3.0x | x | x | x | 1x | 2x | 3x | 4x | 5x | 6x | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | bar: 24
Gatts2 (UA, living room) | 5048 | RR | AS | JJ | ICU | 35000 | 10 | 3.5 | 8 | 4.375 | 2018-03-20 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [13 empty] | 3/16 | D | D | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | RR out | RR out | 3.5x | 3.5x | 3.5x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 4.375 |  | 49: 4.375; 50: 4.375; 51: 4.375; 52: 4.375; 1: 4.375; 2: 4.375; 3: 4.375
Payton (UA, basement) | 5069 | RR | LW | MF | ICU | 80000 | 11 | 7.2727 | 8 | 10 | 2018-06-20 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [24 empty] | 5/29 | D | D | 7.3x | 7.3x | 7.3x | 7.3x | 7.3x | 7.3x | 7.3x | 7.3x | 7.3x | 7.3x | 7.3x | 4x | 5x | 6x | 7x | 8x | 9x | 10x | [7 empty] | 9: 10; 10: 10; 11: 10; 12: 10; 13: 10; 14: 10; 15: 10; 16: 10
Kennah (Garage, Old Town East) | 3914 | WS | AS | JC | ICU | 85000 | 9 | 9.4444 | 10 | 8.5 | [55 empty] | 9.4x | 9.4x | 9.4x | 9.4x | 9.4x | 9.4x | 9.4x | 9.4x | 9.4x | 1x | 2x | 3x | 4x | 5x | 6x | 7x | 8x | 9x | 8.5 |  | 49: 8.5; 50: 8.5; 51: 8.5; 52: 8.5; 1: 8.5; 2: 8.5; 3: 8.5; 4: 8.5; 5: 8.5
Kelleher/Waller (Old Towne East Laundry addition) ASAP | 5092 | RR | LW | ?? | ICU | 45000 | 13 | 3.4615 | 6 | 7.5 | 2018-09-15 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [40 empty] | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x | 3.5x |  | 49: 3.5x; 50: 3.5x; 51: 1x; 52: 2x; 1: 3x; 2: 4x; 3: 5x; 4: 6x; 5: 7x; 7: 7.5; 8: 7.5; 9: 7.5; 10: 7.5; 11: 7.5; 12: 7.5
Fulop Basement | 5066 | RR | AM | MF | ICU | 130000 | 10 | 13 | 17 | 7.6471 | 2018-11-27 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [50 empty] | 7.65x | 13x | 49: 13x; 50: 13x; 51: 13x; 52: 13x; 1: 13x; 2: 13x; 3: 13x; 4: 13x; 5: 13x; 6: 13x; 7: 13x; 8: 13x; 9: 13x; 10: 13x; 11: 13x; 15: 7.6471; 16: 7.6471; 17: 7.6471; 18: 7.6471; 19: 7.6471; 20: 7.6471; 21: 7.6471; 22: 7.6471; 23: 7.6471; 24: 7.6471; 25: 7.6471
Valentine (Hilliard Addition) | 5084 | RR | LW | JJ | ICU | 150000 | 24 | 6.25 | 14 | 10.7143 | 2018-10-19 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [44 empty] | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 6.3x | 1x | 2x | 3x | 4x | 5x | 6x | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143 | 10.7143
Rich/Sullivan | 4180 | JS | OM | ?? | ICU | 150000 | 10 | 15 | 15 | 10 | [75 empty] | 49: 15x; 50: 15x; 51: 15x; 52: 15x; 1: 15x; 2: 15x; 3: 15x; 4: 15x; 5: 15x; 6: 15x; 7: 1x; 8: 2x; 9: 3x; 10: 4x; 11: 5x; 12: 6x; 13: 7x; 19: 10; 20: 10; 21: 10; 22: 10; 23: 10; 24: 10; 25: 10; 26: 10; 27: 10; 28: 10; 29: 10; 30: 10; 31: 10; 32: 10; 33: 10
Dilenschnieder | 6061 | JS | AM | ?? | ICU | 75000 | 9 | 8.3333 | 10 | 7.5 | 2018-12-11 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 50: DA; 51: DA; 52: DA; 1: DA; 2: DA; 3: DA; 4: DA; 5: DA; 6: DA; 7: 1x; 8: 2x; 9: 3x; 10: 4x; 11: 5x; 12: 6x; 15: 7.5; 16: 7.5; 17: 7.5; 18: 7.5; 19: 7.5; 20: 7.5; 21: 7.5; 22: 7.5; 23: 7.5
Woods (Powell) | 5114 | RR | OM | MF | ICU | 100000 | 19 | 5.2632 | 12 | 8.3333 | [81 empty] | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 5.3x | 1x | 2x | 3x | 4x | 5x | 6x | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333
Guiliani (UA) | 4245 | JB | AM | ?? | ICU | 50000 | 8 | 6.25 | 6 | 8.3333 | [75 empty] | 14: 6.3x; 15: 6.3x; 16: 6.3x; 17: 6.3x; 18: 6.3x; 19: 6.3x; 20: 6.3x; 21: 6.3x; 22: 1x; 23: 2x; 24: 3x; 25: 4x; 26: 5x; 27: 6x; 28: 8.3333; 29: 8.3333; 30: 8.3333; 31: 8.3333; 32: 8.3333; 33: 8.3333
Wulf (Dublin) | 3934 | JB | OM | ?? | ICU | 60000 | 22 | 2.7273 | 7 | 8.5714 | [75 empty] | 12: x; 13: x; 14: x; 15: x; 16: x; 17: x; 18: x; 19: x; 20: x; 21: x; 22: x; 23: x; 24: x; 25: x; 26: x; 27: x; 28: x; 29: x; 30: x; 31: x; 32: x; 33: x; 34: 1x; 35: 2x; 36: 3x; 37: 4x; 38: 8.5714; 39: 8.5714; 40: 8.5714; 41: 8.5714; 42: 8.5714; 43: 8.5714
Compston (UA) | 3929 | JC | AM | ?? | ICU | 70000 | 9 | 7.7778 | 8 | 8.75 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 14: x; 15: x; 16: x; 17: x; 18: x; 19: x; 20: x; 21: x; 22: x; 23: x; 24: x; 25: 3x; 26: 4x; 27: 5x; 28: 6x; 29: 7x; 30: 8.75; 31: 8.75; 32: 8.75; 33: 8.75; 34: 8.75; 35: 8.75; 36: 8.75; 37: 8.75
Civilietto | 4240 | JB | LW | ?? | ICU | 60000 | 13 | 4.6154 | 7 | 8.5714 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 19: x; 20: x; 21: x; 22: x; 23: x; 24: x; 25: x; 26: x; 27: x; 28: x; 29: x; 30: x; 31: CC; 32: 1x; 33: 2x; 34: 3x; 35: 4x; 36: 5x; 37: 8.5714; 38: 8.5714; 39: 8.5714; 40: 8.5714; 41: 8.5714; 42: 8.5714; 43: 8.5714
Graver | 4269 | JC | LW | ?? | ICU | 100000 | 10 | 10 | 8 | 12.5 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 21: x; 22: 6.0x; 23: 6.0x; 24: 6.0x; 25: 6.0x; 26: 6.0x; 27: 6.0x; 28: x; 29: x; 30: CC; 31: 1x; 32: 2x; 33: 3x; 34: 4x; 35: 5x; 36: 6x; 37: 7x; 38: 8x; 39: 9x; 40: 12.5; 41: 12.5; 42: 12.5; 43: 12.5; 44: 12.5; 45: 12.5; 46: 12.5; 47: 12.5
Krupp (Worthington) | 3926 | JB | LW | ?? | ICU | 35000 | 19 | 1.8421 | 5 | 7 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 11: x; 12: x; 13: x; 14: x; 15: x; 16: x; 17: x; 18: x; 19: x; 20: x; 21: x; 22: x; 23: x; 24: x; 25: x; 26: CC; 27: x; 28: x; 29: CC; 30: 1x; 31: 2x; 32: 3x; 33: 4x; 34: 5x; 35: 6x; 36: 7x; 37: 8x; 38: 9x; 39: 10x; 40: 7; 41: 7; 42: 7; 43: 7; 44: 7
Anderson | 6119 | JB | ?? | JJ | ICU | 200000 | 8 | 25 | 12 | 16.6667 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 31: x; 32: x; 33: x; 34: x; 35: x; 36: x; 37: x; 38: x; 39: x; 40: CC; 41: 1x; 42: 2x; 43: 3x; 44: 4x; 45: 5x; 46: 16.6667; 47: 16.6667; 48: 16.6667; 49: 16.6667; 50: 16.6667; 51: 16.6667; 52: 16.6667; 1: 16.6667 | 16.6667 | 16.6667 | 16.6667 | 16.6667
Buster (UA) | 5128 | RR | OKM | JJ | ICU | 100000 | 12 | 8.3333 | 12 | 8.3333 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [71 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | CC | 1x | 2x | 3x | 4x | 5x | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333 | 8.3333
Obrien | 5126 | RR | AM | EI | ICU | 80000 | 9 | 8.8889 | 8 | 10 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [60 empty] | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | 8.9x | x | x | x | x | CC | 1x | 2x | 3x | 4x | 5x | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Chowdhury | 4291 | JC | LW | JJ | ICU | 100000 | 10 | 10 | 12 | 8.3333 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [52 empty] | 31: x; 32: x; 33: x; 34: x; 35: x; 36: CC; 37: 1x; 38: 2x; 39: 3x; 40: 4x; 41: 5x; 42: 8.3333; 43: 8.3333; 44: 8.3333; 45: 8.3333; 46: 8.3333; 47: 8.3333; 48: 8.3333; 49: 8.3333; 50: 8.3333; 51: 8.3333; 52: 8.3333; 1: 8.3333
Daneault (Gahanna, 1st Floor remodel) | 4126 | MG | AS |  | P | 200000 | 14 | 14.2857 | 18 | 11.1111 | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [25 empty] | 6/7 | D | D | D | D | 14.3x | 14.3x | 14.3x | 14.3x | 14.3x | 14.3x | 14.3x | 14.3x | 14.3x | 14.3x | 14.3x | 14.3x | 14.3x | 14.3x | bar: 24
Marshall (Westerville, 4 car detached garage) | 5077 | RR | LW | ?? | P | 175000 | [14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0% | [31 empty] | 7/18 | bar: 24
Note on K1: Aaron Enfinger: The total for $ per week of production should not be lower than $8K
Note on S79: Jeff Steele: Shower door
Note on S80: Jeff Steele: T&G ceiling gate
Note on S84: Jeff Steele: Cabinet Changes Master Bath Porch skylights Refinish flooring Electric changes
Note on S87: Jeff Steele: Floor Plan change
Note on S88: Jeff Steele: Stair tread material miscellaneous fireplace changes
Note on S97: Jeff Steele: Structural in old garage New footing @ old garage
Note on F222: Aaron Enfinger: Lost from Deposit

## Totals
Row Labels | Sum of Contract Ttl | 2018 Goal | Needed | Date | Weeks remaining | 2019 Goal | Needed | Total | Weeks remaining
CC | 1939459 | 5500000 | 3560541 | 2019-10-02 | 13 | 6500000 | 6500000 | 2019-10-02 | 52
CLSD | 6508986 |  | 273.8878 |  |  |  | 125
DA | 2380000
LOST | 3115000
P | 930000
(blank)
Formulas:
Total = [Date]

## Actual vs Projected
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
| Week | 01/07/19-01/13/19 | 01/14/19-01/20/19 | 01/21/19-01/27/19 | 01/28/19-02/03/19 | 02/04/19-02/10/19 | 02/11/19-02/17/19 | 02/18/19-02/24/19 | 02/25/19-03/03/19 | 03/04/19-03/10/19 | 03/11/19-03/17/19 | 03/18/19-03/24/19 | 03/25/19-03/31/19 | 04/01/19-04/07/19 | 04/08/19-04/14/19 | 04/15/19-04/21/19 | 04/22/19-04/28/19 | 04/29/19-05/05/19 | 05/06/19-05/12/19 | 05/13/19-05/19/19 | 05/20/19-05/26/19 | 05/27/19-06/02/19 | 06/03/19-06/09/19 | 06/10/19-06/16/19 | 06/17/19-06/23/19 | 06/24/19-06/30/19 | 07/01/19-07/07/19 | 07/08/19-07/14/19 | 07/15/19-07/21/19 | 07/22/19-07/28/19 | 07/29/19-08/04/19 | 08/05/19-08/11/19 | 08/12/19-08/18/19 | 08/19/19-08/25/19 | 08/26/19-09/01/19 | 09/02/19-09/08/19 | 09/09/19-09/15/19 | 09/16/19-09/22/19 | 09/23/19-09/29/19 | 09/30/19-10/06/19 | 10/07/19-10/13/19 | 10/14/19-10/20/19 | 10/21/19-10/27/19 | 10/28/19-11/03/19 | 11/04/19-11/10/19 | 11/11/19-11/17/19 | 11/18/19-11/24/19 | 11/25/19-12/01/19 | 12/02/19-12/08/19 | 12/09/19-12/15/19 | 12/16/19-12/22/19 | 12/23/19-12/29/19 | 12/30/19-01/05/20
| Actual | 31.3504 | 31.3504 | 40.5812 | 40.5812 | 40.5812 | 45.5812 | 54.3858 | 61.0525 | 61.0525 | 75.3308 | 75.3308 | 75.3308 | 75.3308 | 81.8299 | 81.8299 | 62.2866 | 47.2866 | 59.6088 | 78.1249 | 68.036 | 73.7604 | 74.5933 | 80.3253 | 66.2104 | 60.4784 | 60.4784 | 67.5472 | 70.9944 | 79.6543 | 79.6543 | 79.6543 | 73.5178 | 107.0846 | 74.7704 | 81.655 | 104.0925 | 103.7835 | 80.3912 | 92.0978 | 101.8784 | 93.6548 | 97.5715 | 116.8565 | 126.1422 | 148.5064 | 157.5064 | 181.054 | 166.4639 | 173.0751 | 181.8251 | 144.623 | 168.3305 | 4555.0735
| Goal | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 6240
| Actual Cumulative | 31.3504 | 62.7009 | 103.2821 | 143.8633 | 184.4445 | 230.0258 | 284.4115 | 345.464 | 406.5165 | 481.8472 | 557.178 | 632.5088 | 707.8396 | 789.6695 | 871.4994 | 933.786 | 981.0726 | 1040.6814 | 1118.8062 | 1186.8423 | 1260.6027 | 1335.196 | 1415.5212 | 1481.7317 | 1542.2101 | 1602.6885 | 1670.2356 | 1741.23 | 1820.8843 | 1900.5385 | 1980.1928 | 2053.7106 | 2160.7952 | 2235.5656 | 2317.2207 | 2421.3132 | 2525.0967 | 2605.4879 | 2697.5857 | 2799.4641 | 2893.119 | 2990.6904 | 3107.5469 | 3233.6891 | 3382.1955 | 3539.7019 | 3720.7559 | 3887.2199 | 4060.2949 | 4242.12 | 4386.743 | 4555.0735
| Goal Cumulative | 120 | 240 | 360 | 480 | 600 | 720 | 840 | 960 | 1080 | 1200 | 1320 | 1440 | 1560 | 1680 | 1800 | 1920 | 2040 | 2160 | 2280 | 2400 | 2520 | 2640 | 2760 | 2880 | 3000 | 3120 | 3240 | 3360 | 3480 | 3600 | 3720 | 3840 | 3960 | 4080 | 4200 | 4320 | 4440 | 4560 | 4680 | 4800 | 4920 | 5040 | 5160 | 5280 | 5400 | 5520 | 5640 | 5760 | 5880 | 6000 | 6120 | 6240
| DELTA | 88.6496 | 177.2991 | 256.7179 | 336.1367 | 415.5555 | 489.9742 | 555.5885 | 614.536 | 673.4835 | 718.1528 | 762.822 | 807.4912 | 852.1604 | 890.3305 | 928.5006 | 986.214 | 1058.9274 | 1119.3186 | 1161.1938 | 1213.1577 | 1259.3973 | 1304.804 | 1344.4788 | 1398.2683 | 1457.7899 | 1517.3115 | 1569.7644 | 1618.77 | 1659.1157 | 1699.4615 | 1739.8072 | 1786.2894 | 1799.2048 | 1844.4344 | 1882.7793 | 1898.6868 | 1914.9033 | 1954.5121 | 1982.4143 | 2000.5359 | 2026.881 | 2049.3096 | 2052.4531 | 2046.3109 | 2017.8045 | 1980.2981 | 1919.2441 | 1872.7801 | 1819.7051 | 1757.88 | 1733.257 | 1684.9265
Summary
Our Goal | 6240
Remaining Weeks | 18
Up to Date: | 2661.4214
DA Pipeline | 777.9385
Actual+Pipeline | 3439.3599
Goal Seek | 2800.6401
New Weekly Goal | 155.5911

## Start Date
Date Range | 12/31/18-01/06/19 | 01/07/19-01/13/19 | 01/14/19-01/20/19 | 01/21/19-01/27/19 | 01/28/19-02/03/19 | 02/04/19-02/10/19 | 02/11/19-02/17/19 | 02/18/19-02/24/19 | 02/25/19-03/03/19 | 03/04/19-03/10/19 | 03/11/19-03/17/19 | 03/18/19-03/24/19 | 03/25/19-03/31/19 | 04/01/19-04/07/19 | 04/08/19-04/14/19 | 04/15/19-04/21/19 | 04/22/19-04/28/19 | 04/29/19-05/05/19 | 05/06/19-05/12/19 | 05/13/19-05/19/19 | 05/20/19-05/26/19 | 05/27/19-06/02/19 | 06/03/19-06/09/19 | 06/10/19-06/16/19 | 06/17/19-06/23/19 | 06/24/19-06/30/19 | 07/01/19-07/07/19 | 07/08/19-07/14/19 | 07/15/19-07/21/19 | 07/22/19-07/28/19 | 07/29/19-08/04/19 | 08/05/19-08/11/19 | 08/12/19-08/18/19 | 08/19/19-08/25/19 | 08/26/19-09/01/19 | 09/02/19-09/08/19 | 09/09/19-09/15/19 | 09/16/19-09/22/19 | 09/23/19-09/29/19 | 09/30/19-10/06/19 | 10/07/19-10/13/19 | 10/14/19-10/20/19 | 10/21/19-10/27/19 | 10/28/19-11/03/19 | 11/04/19-11/10/19 | 11/11/19-11/17/19 | 11/18/19-11/24/19 | 11/25/19-12/01/19 | 12/02/19-12/08/19 | 12/09/19-12/15/19 | 12/16/19-12/22/19 | 12/23/19-12/29/19 | 12/30/19-01/05/20
Contract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 13.2338 | 23.0824 | 31.3261 | 34.0928 | 48.0462 | 74.8922 | 80.5946 | 80.3912 | 92.0978 | 101.8784 | 93.6548 | 97.5715 | 97.0231 | 97.0231 | 88.554 | 88.554 | 80.054 | 51.1782 | 51.1782 | 51.1782 | 41.3095 | 24.392 | 24.392
All Potential | 161.1554 | 161.1554 | 179.617 | 175.242 | 152.6132 | 135.6067 | 154.0492 | 154.3817 | 164.3817 | 182.2241 | 182.2241 | 178.1616 | 170.6616 | 183.6598 | 198.8068 | 149.7203 | 109.7203 | 134.3646 | 192.1111 | 171.9334 | 183.3822 | 198.2817 | 209.7457 | 174.016 | 162.552 | 154.9049 | 169.0424 | 192.6035 | 209.9233 | 218.6733 | 227.0066 | 224.5823 | 289.2453 | 209.0503 | 236.7729 | 308.4939 | 313.8163 | 266.6499 | 301.7696 | 360.6115 | 335.9407 | 356.024 | 413.879 | 424.5932 | 484.6859 | 528.3525 | 598.9954 | 542.7252 | 562.5585 | 588.8085 | 477.2024 | 539.9916 | 174.9972
Goal | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125

## wrk wk
2018-12-31 | 52
2019-01-01 | 52
2019-01-02 | 52
2019-01-03 | 52
2019-01-04 | 52
2019-01-05 | 52
2019-01-06 | 52
2019-01-07 | 52
2019-01-08 | 51
2019-01-09 | 51
2019-01-10 | 51
2019-01-11 | 51
2019-01-12 | 51
2019-01-13 | 51
2019-01-14 | 51
2019-01-15 | 50
2019-01-16 | 50
2019-01-17 | 50
2019-01-18 | 50
2019-01-19 | 50
2019-01-20 | 50
2019-01-21 | 50
2019-01-22 | 49
2019-01-23 | 49
2019-01-24 | 49
2019-01-25 | 49
2019-01-26 | 49
2019-01-27 | 49
2019-01-28 | 49
2019-01-29 | 48
2019-01-30 | 48
2019-01-31 | 48
2019-02-01 | 48
2019-02-02 | 48
2019-02-03 | 48
2019-02-04 | 48
2019-02-05 | 47
2019-02-06 | 47
2019-02-07 | 47
2019-02-08 | 47
2019-02-09 | 47
2019-02-10 | 47
2019-02-11 | 47
2019-02-12 | 46
2019-02-13 | 46
2019-02-14 | 46
2019-02-15 | 46
2019-02-16 | 46
2019-02-17 | 46
2019-02-18 | 46
2019-02-19 | 45
2019-02-20 | 45
2019-02-21 | 45
2019-02-22 | 45
2019-02-23 | 45
2019-02-24 | 45
2019-02-25 | 45
2019-02-26 | 44
2019-02-27 | 44
2019-02-28 | 44
2019-03-01 | 44
2019-03-02 | 44
2019-03-03 | 44
2019-03-04 | 44
2019-03-05 | 43
2019-03-06 | 43
2019-03-07 | 43
2019-03-08 | 43
2019-03-09 | 43
2019-03-10 | 43
2019-03-11 | 43
2019-03-12 | 42
2019-03-13 | 42
2019-03-14 | 42
2019-03-15 | 42
2019-03-16 | 42
2019-03-17 | 42
2019-03-18 | 42
2019-03-19 | 41
2019-03-20 | 41
2019-03-21 | 41
2019-03-22 | 41
2019-03-23 | 41
2019-03-24 | 41
2019-03-25 | 41
2019-03-26 | 40
2019-03-27 | 40
2019-03-28 | 40
2019-03-29 | 40
2019-03-30 | 40
2019-03-31 | 40
2019-04-01 | 40
2019-04-02 | 39
2019-04-03 | 39
2019-04-04 | 39
2019-04-05 | 39
2019-04-06 | 39
2019-04-07 | 39
2019-04-08 | 39
2019-04-09 | 38
2019-04-10 | 38
2019-04-11 | 38
2019-04-12 | 38
2019-04-13 | 38
2019-04-14 | 38
2019-04-15 | 38
2019-04-16 | 37
2019-04-17 | 37
2019-04-18 | 37
2019-04-19 | 37
2019-04-20 | 37
2019-04-21 | 37
2019-04-22 | 37
2019-04-23 | 36
2019-04-24 | 36
2019-04-25 | 36
2019-04-26 | 36
2019-04-27 | 36
2019-04-28 | 36
2019-04-29 | 36
2019-04-30 | 35
2019-05-01 | 35
2019-05-02 | 35
2019-05-03 | 35
2019-05-04 | 35
2019-05-05 | 35
2019-05-06 | 35
2019-05-07 | 34
2019-05-08 | 34
2019-05-09 | 34
2019-05-10 | 34
2019-05-11 | 34
2019-05-12 | 34
2019-05-13 | 34
2019-05-14 | 33
2019-05-15 | 33
2019-05-16 | 33
2019-05-17 | 33
2019-05-18 | 33
2019-05-19 | 33
2019-05-20 | 33
2019-05-21 | 32
2019-05-22 | 32
2019-05-23 | 32
2019-05-24 | 32
2019-05-25 | 32
2019-05-26 | 32
2019-05-27 | 32
2019-05-28 | 31
2019-05-29 | 31
2019-05-30 | 31
2019-05-31 | 31
2019-06-01 | 31
2019-06-02 | 31
2019-06-03 | 31
2019-06-04 | 30
2019-06-05 | 30
2019-06-06 | 30
2019-06-07 | 30
2019-06-08 | 30
2019-06-09 | 30
2019-06-10 | 30
2019-06-11 | 29
2019-06-12 | 29
2019-06-13 | 29
2019-06-14 | 29
2019-06-15 | 29
2019-06-16 | 29
2019-06-17 | 29
2019-06-18 | 28
2019-06-19 | 28
2019-06-20 | 28
2019-06-21 | 28
2019-06-22 | 28
2019-06-23 | 28
2019-06-24 | 28
2019-06-25 | 27
2019-06-26 | 27
2019-06-27 | 27
2019-06-28 | 27
2019-06-29 | 27
2019-06-30 | 27
2019-07-01 | 27
2019-07-02 | 26
2019-07-03 | 26
2019-07-04 | 26
2019-07-05 | 26
2019-07-06 | 26
2019-07-07 | 26
2019-07-08 | 26
2019-07-09 | 25
2019-07-10 | 25
2019-07-11 | 25
2019-07-12 | 25
2019-07-13 | 25
2019-07-14 | 25
2019-07-15 | 25
2019-07-16 | 24
2019-07-17 | 24
2019-07-18 | 24
2019-07-19 | 24
2019-07-20 | 24
2019-07-21 | 24
2019-07-22 | 24
2019-07-23 | 23
2019-07-24 | 23
2019-07-25 | 23
2019-07-26 | 23
2019-07-27 | 23
2019-07-28 | 23
2019-07-29 | 23
2019-07-30 | 22
2019-07-31 | 22
2019-08-01 | 22
2019-08-02 | 22
2019-08-03 | 22
2019-08-04 | 22
2019-08-05 | 22
2019-08-06 | 21
2019-08-07 | 21
2019-08-08 | 21
2019-08-09 | 21
2019-08-10 | 21
2019-08-11 | 21
2019-08-12 | 21
2019-08-13 | 20
2019-08-14 | 20
2019-08-15 | 20
2019-08-16 | 20
2019-08-17 | 20
2019-08-18 | 20
2019-08-19 | 20
2019-08-20 | 19
2019-08-21 | 19
2019-08-22 | 19
2019-08-23 | 19
2019-08-24 | 19
2019-08-25 | 19
2019-08-26 | 19
2019-08-27 | 18
2019-08-28 | 18
2019-08-29 | 18
2019-08-30 | 18
2019-08-31 | 18
2019-09-01 | 18
2019-09-02 | 18
2019-09-03 | 17
2019-09-04 | 17
2019-09-05 | 17
2019-09-06 | 17
2019-09-07 | 17
2019-09-08 | 17
2019-09-09 | 17
2019-09-10 | 16
2019-09-11 | 16
2019-09-12 | 16
2019-09-13 | 16
2019-09-14 | 16
2019-09-15 | 16
2019-09-16 | 16
2019-09-17 | 15
2019-09-18 | 15
2019-09-19 | 15
2019-09-20 | 15
2019-09-21 | 15
2019-09-22 | 15
2019-09-23 | 15
2019-09-24 | 14
2019-09-25 | 14
2019-09-26 | 14
2019-09-27 | 14
2019-09-28 | 14
2019-09-29 | 14
2019-09-30 | 14
2019-10-01 | 13
2019-10-02 | 13
2019-10-03 | 13
2019-10-04 | 13
2019-10-05 | 13
2019-10-06 | 13
2019-10-07 | 13
2019-10-08 | 12
2019-10-09 | 12
2019-10-10 | 12
2019-10-11 | 12
2019-10-12 | 12
2019-10-13 | 12
2019-10-14 | 12
2019-10-15 | 11
2019-10-16 | 11
2019-10-17 | 11
2019-10-18 | 11
2019-10-19 | 11
2019-10-20 | 11
2019-10-21 | 11
2019-10-22 | 10
2019-10-23 | 10
2019-10-24 | 10
2019-10-25 | 10
2019-10-26 | 10
2019-10-27 | 10
2019-10-28 | 10
2019-10-29 | 9
2019-10-30 | 9
2019-10-31 | 9
2019-11-01 | 9
2019-11-02 | 9
2019-11-03 | 9
2019-11-04 | 9
2019-11-05 | 8
2019-11-06 | 8
2019-11-07 | 8
2019-11-08 | 8
2019-11-09 | 8
2019-11-10 | 8
2019-11-11 | 8
2019-11-12 | 7
2019-11-13 | 7
2019-11-14 | 7
2019-11-15 | 7
2019-11-16 | 7
2019-11-17 | 7
2019-11-18 | 7
2019-11-19 | 6
2019-11-20 | 6
2019-11-21 | 6
2019-11-22 | 6
2019-11-23 | 6
2019-11-24 | 6
2019-11-25 | 6
2019-11-26 | 5
2019-11-27 | 5
2019-11-28 | 5
2019-11-29 | 5
2019-11-30 | 5
2019-12-01 | 5
2019-12-02 | 5
2019-12-03 | 4
2019-12-04 | 4
2019-12-05 | 4
2019-12-06 | 4
2019-12-07 | 4
2019-12-08 | 4
2019-12-09 | 4
2019-12-10 | 3
2019-12-11 | 3
2019-12-12 | 3
2019-12-13 | 3
2019-12-14 | 3
2019-12-15 | 3
2019-12-16 | 3
2019-12-17 | 2
2019-12-18 | 2
2019-12-19 | 2
2019-12-20 | 2
2019-12-21 | 2
2019-12-22 | 2
2019-12-23 | 2
2019-12-24 | 1
2019-12-25 | 1
2019-12-26 | 1
2019-12-27 | 1
2019-12-28 | 1
2019-12-29 | 1
2019-12-30 | 1
2019-12-31 | 52
2020-01-01 | 52
2020-01-02 | 52
2020-01-03 | 52
2020-01-04 | 52
2020-01-05 | 52
2020-01-06 | 52
2020-01-07 | 51
2020-01-08 | 51
2020-01-09 | 51
2020-01-10 | 51
2020-01-11 | 51
2020-01-12 | 51
2020-01-13 | 51
2020-01-14 | 50
2020-01-15 | 50
2020-01-16 | 50
2020-01-17 | 50
2020-01-18 | 50
2020-01-19 | 50
2020-01-20 | 50
2020-01-21 | 49
2020-01-22 | 49
2020-01-23 | 49
2020-01-24 | 49
2020-01-25 | 49
2020-01-26 | 49
2020-01-27 | 49
2020-01-28 | 48
2020-01-29 | 48
2020-01-30 | 48
2020-01-31 | 48
2020-02-01 | 48
2020-02-02 | 48
2020-02-03 | 48
2020-02-04 | 47
2020-02-05 | 47
2020-02-06 | 47
2020-02-07 | 47
2020-02-08 | 47
2020-02-09 | 47
2020-02-10 | 47
2020-02-11 | 46
2020-02-12 | 46
2020-02-13 | 46
2020-02-14 | 46
2020-02-15 | 46
2020-02-16 | 46
2020-02-17 | 46
2020-02-18 | 45
2020-02-19 | 45
2020-02-20 | 45
2020-02-21 | 45
2020-02-22 | 45
2020-02-23 | 45
2020-02-24 | 45
2020-02-25 | 44
2020-02-26 | 44
2020-02-27 | 44
2020-02-28 | 44
2020-02-29 | 44
2020-03-01 | 44
2020-03-02 | 44
2020-03-03 | 43
2020-03-04 | 43
2020-03-05 | 43
2020-03-06 | 43
2020-03-07 | 43
2020-03-08 | 43
2020-03-09 | 43
2020-03-10 | 42
2020-03-11 | 42
2020-03-12 | 42
2020-03-13 | 42
2020-03-14 | 42
2020-03-15 | 42
2020-03-16 | 42
2020-03-17 | 41
2020-03-18 | 41
2020-03-19 | 41
2020-03-20 | 41
2020-03-21 | 41
2020-03-22 | 41
2020-03-23 | 41
2020-03-24 | 40
2020-03-25 | 40
2020-03-26 | 40
2020-03-27 | 40
2020-03-28 | 40
2020-03-29 | 40
2020-03-30 | 40
2020-03-31 | 39
2020-04-01 | 39
2020-04-02 | 39
2020-04-03 | 39
2020-04-04 | 39
2020-04-05 | 39
2020-04-06 | 39
2020-04-07 | 38
2020-04-08 | 38
2020-04-09 | 38
2020-04-10 | 38
2020-04-11 | 38
2020-04-12 | 38
2020-04-13 | 38
2020-04-14 | 37
2020-04-15 | 37
2020-04-16 | 37
2020-04-17 | 37
2020-04-18 | 37
2020-04-19 | 37
2020-04-20 | 37
2020-04-21 | 36
2020-04-22 | 36
2020-04-23 | 36
2020-04-24 | 36
2020-04-25 | 36
2020-04-26 | 36
2020-04-27 | 36
2020-04-28 | 35
2020-04-29 | 35
2020-04-30 | 35
2020-05-01 | 35
2020-05-02 | 35
2020-05-03 | 35
2020-05-04 | 35
2020-05-05 | 34
2020-05-06 | 34
2020-05-07 | 34
2020-05-08 | 34
2020-05-09 | 34
2020-05-10 | 34
2020-05-11 | 34
2020-05-12 | 33
2020-05-13 | 33
2020-05-14 | 33
2020-05-15 | 33
2020-05-16 | 33
2020-05-17 | 33
2020-05-18 | 33
2020-05-19 | 32
2020-05-20 | 32
2020-05-21 | 32
2020-05-22 | 32
2020-05-23 | 32
2020-05-24 | 32
2020-05-25 | 32
2020-05-26 | 31
2020-05-27 | 31
2020-05-28 | 31
2020-05-29 | 31
2020-05-30 | 31
2020-05-31 | 31
2020-06-01 | 31
2020-06-02 | 30
2020-06-03 | 30
2020-06-04 | 30
2020-06-05 | 30
2020-06-06 | 30
2020-06-07 | 30
2020-06-08 | 30
2020-06-09 | 29
2020-06-10 | 29
2020-06-11 | 29
2020-06-12 | 29
2020-06-13 | 29
2020-06-14 | 29
2020-06-15 | 29
2020-06-16 | 28
2020-06-17 | 28
2020-06-18 | 28
2020-06-19 | 28
2020-06-20 | 28
2020-06-21 | 28
2020-06-22 | 28
2020-06-23 | 27
2020-06-24 | 27
2020-06-25 | 27
2020-06-26 | 27
2020-06-27 | 27
2020-06-28 | 27
2020-06-29 | 27
2020-06-30 | 26
2020-07-01 | 26
2020-07-02 | 26
2020-07-03 | 26
2020-07-04 | 26
2020-07-05 | 26
2020-07-06 | 26
2020-07-07 | 25
2020-07-08 | 25
2020-07-09 | 25
2020-07-10 | 25
2020-07-11 | 25
2020-07-12 | 25
2020-07-13 | 25
2020-07-14 | 24
2020-07-15 | 24
2020-07-16 | 24
2020-07-17 | 24
2020-07-18 | 24
2020-07-19 | 24
2020-07-20 | 24
2020-07-21 | 23
2020-07-22 | 23
2020-07-23 | 23
2020-07-24 | 23
2020-07-25 | 23
2020-07-26 | 23
2020-07-27 | 23
2020-07-28 | 22
2020-07-29 | 22
2020-07-30 | 22
2020-07-31 | 22
2020-08-01 | 22
2020-08-02 | 22
2020-08-03 | 22
2020-08-04 | 21
2020-08-05 | 21
2020-08-06 | 21
2020-08-07 | 21
2020-08-08 | 21
2020-08-09 | 21
2020-08-10 | 21
2020-08-11 | 20
2020-08-12 | 20
2020-08-13 | 20
2020-08-14 | 20
2020-08-15 | 20
2020-08-16 | 20
2020-08-17 | 20
2020-08-18 | 19
2020-08-19 | 19
2020-08-20 | 19
2020-08-21 | 19
2020-08-22 | 19
2020-08-23 | 19
2020-08-24 | 19
2020-08-25 | 18
2020-08-26 | 18
2020-08-27 | 18
2020-08-28 | 18
2020-08-29 | 18
2020-08-30 | 18
2020-08-31 | 18
2020-09-01 | 17
2020-09-02 | 17
2020-09-03 | 17
2020-09-04 | 17
2020-09-05 | 17
2020-09-06 | 17
2020-09-07 | 17
2020-09-08 | 16
2020-09-09 | 16
2020-09-10 | 16
2020-09-11 | 16
2020-09-12 | 16
2020-09-13 | 16
2020-09-14 | 16
2020-09-15 | 15
2020-09-16 | 15
2020-09-17 | 15
2020-09-18 | 15
2020-09-19 | 15
2020-09-20 | 15
2020-09-21 | 15
2020-09-22 | 14
2020-09-23 | 14
2020-09-24 | 14
2020-09-25 | 14
2020-09-26 | 14
2020-09-27 | 14
2020-09-28 | 14
2020-09-29 | 13
2020-09-30 | 13
2020-10-01 | 13
2020-10-02 | 13
2020-10-03 | 13
2020-10-04 | 13
2020-10-05 | 13
2020-10-06 | 12
2020-10-07 | 12
2020-10-08 | 12
2020-10-09 | 12
2020-10-10 | 12
2020-10-11 | 12
2020-10-12 | 12
2020-10-13 | 11
2020-10-14 | 11
2020-10-15 | 11
2020-10-16 | 11
2020-10-17 | 11
2020-10-18 | 11
2020-10-19 | 11
2020-10-20 | 10
2020-10-21 | 10
2020-10-22 | 10
2020-10-23 | 10
2020-10-24 | 10
2020-10-25 | 10
2020-10-26 | 10
2020-10-27 | 9
2020-10-28 | 9
2020-10-29 | 9
2020-10-30 | 9
2020-10-31 | 9
2020-11-01 | 9
2020-11-02 | 9
2020-11-03 | 8
2020-11-04 | 8
2020-11-05 | 8
2020-11-06 | 8
2020-11-07 | 8
2020-11-08 | 8
2020-11-09 | 8
2020-11-10 | 7
2020-11-11 | 7
2020-11-12 | 7
2020-11-13 | 7
2020-11-14 | 7
2020-11-15 | 7
2020-11-16 | 7
2020-11-17 | 6
2020-11-18 | 6
2020-11-19 | 6
2020-11-20 | 6
2020-11-21 | 6
2020-11-22 | 6
2020-11-23 | 6
2020-11-24 | 5
2020-11-25 | 5
2020-11-26 | 5
2020-11-27 | 5
2020-11-28 | 5
2020-11-29 | 5
2020-11-30 | 5
2020-12-01 | 4
2020-12-02 | 4
2020-12-03 | 4
2020-12-04 | 4
2020-12-05 | 4
2020-12-06 | 4
2020-12-07 | 4
2020-12-08 | 3
2020-12-09 | 3
2020-12-10 | 3
2020-12-11 | 3
2020-12-12 | 3
2020-12-13 | 3
2020-12-14 | 3
2020-12-15 | 2
2020-12-16 | 2
2020-12-17 | 2
2020-12-18 | 2
2020-12-19 | 2
2020-12-20 | 2
2020-12-21 | 2
2020-12-22 | 1
2020-12-23 | 1
2020-12-24 | 1
2020-12-25 | 1
2020-12-26 | 1
2020-12-27 | 1
2020-12-28 | 1
2020-12-29
2020-12-30
2020-12-31
2021-01-01
2021-01-02
2021-01-03
2021-01-04
2021-01-05
2021-01-06
2021-01-07
2021-01-08
2021-01-09
2021-01-10
2021-01-11
2021-01-12
2021-01-13
2021-01-14
2021-01-15
2021-01-16